WASEL

Complete Execution Timeline & Costed Roadmap

Year 1 · February 2026 – February 2027

CONFIDENTIAL — For Internal & Investor Use Only

"To move Jordan forward — fairly."

| Document Version | 1.0 |
| --- | --- |
| Prepared by | Wasel Founding Team |
| Date | February 2026 |
| Review Cycle | Monthly — updated after each Stage Gate |
| Total Planned Budget (Year 1) | JD 472,000 (~$665K) |
| Seed Round Target | JD 472,000 |
| Planned Launch Date | Late August 2026 |
| Year-End Target Drivers | 500+ active |
| Year-End Target Riders | 8,000+ registered |

# Table of Contents

Table of Contents	2

1. Executive Summary	3

2. Key Assumptions	4

3. Workstreams & Owners	6

4. Phase Plan & Stage Gates	7

5. Week-by-Week Execution Plan	8

6. Cost Model & Budget Breakdown	13

7. KPI Dashboard Specification	14

8. Risk Register	16

9. Launch Playbook — Day -14 to Day +14	17

10. Final Deliverables Checklist	19

11. Appendix: Notes & Definitions	21

# 1. Executive Summary

Wasel is Jordan's first subscription-based ride-hailing platform, designed to replace the Uber/Careem commission model with a fair, flat monthly fee for drivers. This document sets out the complete Year 1 execution plan — from incorporation through full Amman launch to Series A preparation — covering all workstreams, owners, timelines, costs, and KPIs.

MISSION & STRATEGIC CONTEXT

Mission: "To move Jordan forward — fairly." Wasel charges drivers a flat JD 20–55/month depending on tier, against the 30% commission extracted by incumbents. At an average of 9 trips/day at JD 2.37/trip, a Wasel Standard driver earns ~JD 91 more per month than an equivalent Uber/Careem driver.

The launch is accelerated by a structural market opportunity: Uber's September 2025 investment in Israeli drone company Flytrex has catalysed a boycott movement among Jordanian consumers and drivers, creating a 1.25x acquisition efficiency multiplier. This tailwind must be captured within the next 12–18 months before it fades.

YEAR 1 FINANCIAL HEADLINES

| Seed Raise Target | JD 472,000 (~$665K USD) |
| --- | --- |
| Year 1 Total Revenue (projected) | JD 284,000 |
| — Driver Subscriptions | JD 154,000 |
| — Rider Subscriptions | JD 130,000 |
| Year 1 Net Operating Loss | JD 726,000 |
| Implied Runway at Raise | ~14 months to Series A gate |
| Fare vs Incumbent | JD 2.37 (5% below Uber/Careem) |
| Driver Tiers | Standard JD 20/mo · Plus JD 35/mo · Pro JD 55/mo |
| Rider Tiers | Wasel Go JD 5/mo · Wasel Pass JD 10/mo (perks, not discounts) |

FIVE PHASES AT A GLANCE

| Phase 0: Foundation | Weeks 1–6 (Feb–Apr 2026) ¦ Legal, incorporation, LTRC licence filing, seed close |
| --- | --- |
| Phase 1: Build | Weeks 7–18 (Apr–Jun 2026) ¦ 10 dev sprints, app stores, team hiring, brand launch |
| Phase 2: Driver Onboarding | Weeks 19–26 (Jun–Aug 2026) ¦ 80+ drivers onboarded; M0 → M1 → M2 cohort ramp |
| Phase 3: Soft Launch | Weeks 27–36 (Aug–Oct 2026) ¦ 500 invite codes; 200+ drivers; 1,000+ riders; NPS tracking |
| Phase 4: Full Launch | Weeks 37–44 (Nov–Dec 2026) ¦ Paid media; 400+ drivers; 5,000+ riders; corporate accounts |
| Phase 5: Scale & Series A | Weeks 45–52 (Jan–Feb 2027) ¦ Zarqa expansion; Series A roadshow; v2.0 planning |

# 2. Key Assumptions

All budget lines, headcount plans, and KPI targets in this document are derived from the following assumptions. These should be reviewed and updated after each Stage Gate.

MARKET & REGULATORY ASSUMPTIONS

| Assumption | Base Case | Stress Case |
| --- | --- | --- |
| LTRC licence granted | Week 12 (May 2026) | Week 16 (Jun 2026) |
| LTRC annual licence fee | JD 100,000/yr | JD 120,000/yr |
| Bank guarantee required | JD 25,000 | JD 25,000 |
| Seed round close | Week 5 (Mar 2026) | Week 8 (Apr 2026) |
| Driver app development | JD 32,000 (10 sprints) | JD 40,000 |
| Boycott tailwind multiplier | 1.25x acq. efficiency | 1.0x (fades by Wk 30) |
| Jordan USD exchange rate | 1 JD = $1.41 USD | 1 JD = $1.41 USD |

DRIVER ECONOMICS ASSUMPTIONS

| Average trips/day (Standard driver) | 8 trips (capped) |
| --- | --- |
| Average fare per trip | JD 2.37 |
| Driver gross daily revenue (Standard) | JD 18.96 |
| Working days per month | 22 days |
| Driver gross monthly revenue (Standard) | JD 417 |
| Driver subscription fee (Standard) | JD 20/month |
| Driver net monthly revenue (Standard) | JD 397 |
| Equivalent Uber/Careem net (30% commission) | JD 306 |
| Wasel driver uplift vs incumbent | +JD 91/month (+30%) |
| M0 (trial) duration | 1 month, free |
| M1 (ramp) fee | JD 10/month |
| M2+ (full tier) activation | Month 3+ |
| Expected M0→M2 conversion rate | 60% |
| Monthly driver churn (steady state) | 8% |

RIDER ECONOMICS ASSUMPTIONS

| Wasel Go monthly fee | JD 5/month |
| --- | --- |
| Wasel Pass monthly fee | JD 10/month |
| Perks model (no fare discounts) | Priority dispatch, surge cap, cancellation flexibility |
| Cost to Wasel per perk delivered | JD 0 (operational, not monetary) |
| Rider MoM growth rate (Wks 27–40) | 25–30% |
| Target riders by end of Year 1 | 8,000 registered / 4,000 active |
| Rider subscription attach rate | 35% of active riders |
| Average rider LTV (Year 1) | JD 42 |

# 3. Workstreams & Owners

All execution activity is organised into seven workstreams, each with a designated owner and supporting resources.

| Workstream | Owner | Key Deliverables | Headcount | Phase Peak | Budget % |
| --- | --- | --- | --- | --- | --- |
| Legal | External Counsel + Founder | LTRC licence, T&Cs, insurance, PDPL | 1 (outsourced) | P0–P1 | 4% |
| Technology | CTO | 10 sprints, app stores, infra scaling | 5–8 (vendor+in-house) | P1 | 26% |
| Operations | COO | Zone mgmt, driver ops, SLA, airport | 3–5 | P3–P4 | 12% |
| Driver Relations | 2× Driver Rel Officers | M0/M1/M2 onboarding, training, retention | 2–4 | P2–P4 | 8% |
| Marketing | Marketing Lead | Brand, campaigns, Fairness Reports, PR, OOH | 2–3 | P3–P4 | 22% |
| Finance | CFO (part-time → full-time P4) | Seed close, reporting, Series A data room | 1–2 | P0, P5 | 6% |
| People & Org | Founder | Hiring, culture, comp benchmarking | 1 | P0, P4 | 22% |

HEADCOUNT BUILD PLAN

| Phase 0 (Feb–Apr 2026) | 3 hires: Ops Manager, CX Lead, Marketing Lead → Total: 4 incl. Founder |
| --- | --- |
| Phase 1 (Apr–Jun 2026) | 3 hires: CTO (or VP Eng), 2 Driver Rel Officers, 1 Data Analyst → Total: 8 |
| Phase 2 (Jun–Aug 2026) | No new hires; consolidate and train existing team |
| Phase 3 (Aug–Oct 2026) | 2 hires: 1 CX Agent, 1 B2B Sales Exec → Total: 10 |
| Phase 4 (Nov–Dec 2026) | 3 hires: 2 Driver Rel Officers, 1 Finance Analyst → Total: 13 |
| Phase 5 (Jan–Feb 2027) | Assessment: 2–3 additional hires pending Series A close |

# 4. Phase Plan & Stage Gates

Execution is divided into six phases (P0–P5). Each phase concludes with a Stage Gate review — a formal go/no-go decision point assessed by the founding team and lead investor. Failing a Stage Gate triggers a 2-week remediation sprint before re-assessment.

| P0 | Foundation ¦ Weeks 1–6 ¦ Feb 23 – Apr 5, 2026 ¦ Budget: JD 8,600 |
| --- | --- |
| Legal incorporation, LTRC application, bank account setup, seed round roadshow launch, vendor selection for app development. Stage Gate 0 (informal): seed round committed, legal structure in place, LTRC application filed. |  |

| P1 | Build ¦ Weeks 7–18 ¦ Apr 6 – Jun 28, 2026 ¦ Budget: JD 62,000 |
| --- | --- |
| 10 development sprints delivering driver app, rider app, admin dashboard, payment integration, and both app store submissions. Team hiring, brand identity finalisation, driver waitlist activation. STAGE GATE 1 (Week 18): apps approved on stores, LTRC licence confirmed, 50+ driver waitlist, team 8 FTE. |  |

| P2 | Driver Onboarding ¦ Weeks 19–26 ¦ Jun 29 – Aug 23, 2026 ¦ Budget: JD 22,000 |
| --- | --- |
| First 30 M0 drivers onboarded (free trial); M0→M1 conversion push; rider pre-registration campaign ("Save Your Seat"); Monthly Fairness Report #1 published; boycott tailwind content activated. STAGE GATE 2 (Week 26): 80+ active drivers, app stable, media coverage secured, 500+ rider pre-signups. |  |

| P3 | Soft Launch ¦ Weeks 27–36 ¦ Aug 24 – Nov 1, 2026 ¦ Budget: JD 48,000 |
| --- | --- |
| Public soft launch with 500 invite codes; war room ops; referral programme; Wasel Pass subscription open; influencer partnerships; v1.1 and v1.2 app releases; driver milestone event. STAGE GATE 3 (Week 36): 200+ active drivers, 1,000+ riders, revenue tracking vs model, NPS > 50. |  |

| P4 | Full Launch ¦ Weeks 37–44 ¦ Nov 2 – Dec 27, 2026 ¦ Budget: JD 98,000 |
| --- | --- |
| Remove invite gates; paid media (Google/Meta/TikTok); OOH campaign (10 Amman billboards); airport corridor activation; corporate accounts programme; Series A data room preparation. STAGE GATE 4 (Week 44): 400+ drivers, 5,000+ riders, monthly revenue JD 35K+, NPS > 60. |  |

| P5 | Scale & Series A ¦ Weeks 45–52 ¦ Dec 28, 2026 – Feb 21, 2027 ¦ Budget: JD 130,000 |
| --- | --- |
| Series A roadshow (15 VC/FO meetings); Zarqa city soft launch; v2.0 planning (Pool, Ladies, AI dispatch); LTRC renewal; annual audit; year-end review. STAGE GATE 5 (Week 52): Series A term sheet received OR bridge financing plan approved; Zarqa stable; 600+ drivers. |  |

# 5. Week-by-Week Execution Plan

The table below details every major task across all 52 weeks. Weeks with multiple parallel workstream activities are listed on separate rows. Phase colour coding: P0 = Amber · P1 = Blue · P2 = Green · P3 = Pink · P4 = Purple · P5 = Red.

| Wk | Dates | Workstream | Key Task / Deliverable | Owner | Budget |
| --- | --- | --- | --- | --- | --- |
| 1 | Feb 23 – Mar 1 | Legal | Incorporate company (Jordan); appoint legal counsel; open corporate bank account | Founder / Legal | JD 500 |
| 1 | Feb 23 – Mar 1 | Finance | Draft fundraising materials; update investor deck with revised model v2 figures | Founder / CFO | — |
| 2 | Mar 2 – Mar 8 | Legal | File LTRC operator licence application; prepare JD 25K bank guarantee documentation | Legal | JD 2,500 |
| 2 | Mar 2 – Mar 8 | Finance | Launch seed round roadshow (target JD 472K / ~$665K); first LP meetings | Founder | — |
| 3 | Mar 9 – Mar 15 | Legal | Register data protection compliance (Jordan PDPL); draft driver & rider T&Cs | Legal | JD 300 |
| 3 | Mar 9 – Mar 15 | Ops | Define Amman pilot zone boundaries (North Amman: Abdoun, Sweifieh, Khalda, 7th Circle) | COO | — |
| 4 | Mar 16 – Mar 22 | Tech | Issue RFPs for app development; evaluate 3 local + 1 offshore vendor; select partner | CTO | — |
| 4 | Mar 16 – Mar 22 | Legal | Finalise employment contracts for founding team hires | HR / Legal | — |
| 5 | Mar 23 – Mar 29 | Finance | Close seed round; wire funds; set up financial reporting cadence | CFO / Founder | — |
| 5 | Mar 23 – Mar 29 | Tech | Sign development contract; kick off sprint planning; set up GitHub, JIRA, Figma workspaces | CTO | JD 1,200 |
| 6 | Mar 30 – Apr 5 | Legal | LTRC follow-up; submit any outstanding documentation; register vehicles list | Legal | JD 500 |
| 6 | Mar 30 – Apr 5 | People | Hire Ops Manager, Customer Experience Lead, Marketing Lead (3 full-time) | Founder | JD 3,600 |
| 7 | Apr 6 – Apr 12 | Tech | Sprint 1: Architecture setup, auth, user registration, map SDK integration | CTO / Dev Team | JD 4,000 |
| 7 | Apr 6 – Apr 12 | Brand | Finalise visual identity: logo, colours, Arabic / English typography; print collateral brief | Marketing | JD 1,500 |
| 8 | Apr 13 – Apr 19 | Tech | Sprint 2: Driver app core — trip request, accept, navigate flow; subscription billing module | Dev Team | JD 4,000 |
| 8 | Apr 13 – Apr 19 | Marketing | Launch driver waitlist landing page; begin social media presence (@WaselJO) | Marketing | JD 600 |
| 9 | Apr 20 – Apr 26 | Tech | Sprint 3: Rider app — booking, real-time tracking, payment integration (CliQ/Visa) | Dev Team | JD 4,000 |
| 9 | Apr 20 – Apr 26 | Ops | Map Amman zones; define service hours (6am–2am); draft driver standard operating procedures | COO | JD 400 |
| 10 | Apr 27 – May 3 | Tech | Sprint 4: Admin dashboard — driver KYC, subscriptions, analytics; notification system (FCM) | Dev Team | JD 4,000 |
| 10 | Apr 27 – May 3 | Marketing | Driver acquisition campaign brief; produce video testimonial concept; community outreach plan | Marketing | JD 800 |
| 11 | May 4 – May 10 | Tech | Sprint 5: Rating & review system; in-app chat; emergency SOS button; accessibility features | Dev Team | JD 4,000 |
| 11 | May 4 – May 10 | Finance | Set up accounting system (QuickBooks); implement payroll for 3 staff; monthly reporting template | CFO | JD 400 |
| 12 | May 11 – May 17 | Tech | Sprint 6: Surge pricing cap logic; Wasel Pass / Wasel Go perk activation; cancellation policy engine | Dev Team | JD 4,000 |
| 12 | May 11 – May 17 | Legal | Receive LTRC licence (expected); sign insurance policy for registered fleet | Legal | JD 2,200 |
| 13 | May 18 – May 24 | Tech | Sprint 7: Full integration testing; load testing (target 500 concurrent); bug backlog triage | Dev + QA | JD 4,000 |
| 13 | May 18 – May 24 | Ops | Driver vehicle inspection protocol; partner with 2 garages for certified inspection service | COO | JD 800 |
| 14 | May 25 – May 31 | Tech | Sprint 8: iOS App Store + Google Play submissions; beta build release (internal) | CTO | JD 4,000 |
| 14 | May 25 – May 31 | Marketing | Branded merch design (car decals, driver uniforms, phone mounts); order print run | Marketing | JD 2,400 |
| 15 | Jun 1 – Jun 7 | Tech | Sprint 9: App Store / Play Store review cycle; address feedback; prepare v1.0 release candidate | Dev + CTO | JD 4,000 |
| 15 | Jun 1 – Jun 7 | Ops | Define driver support SLA (response <2h, resolution <24h); set up WhatsApp Business helpline | Ops Manager | JD 300 |
| 16 | Jun 8 – Jun 14 | Tech | Sprint 10: Final UAT with 10 internal testers; fix all P0/P1 bugs; tag v1.0.0 | QA / Dev | JD 4,000 |
| 16 | Jun 8 – Jun 14 | Finance | Board update; investor monthly report #1; revise cash flow with actual spend vs budget | CFO | — |
| 17 | Jun 15 – Jun 21 | People | Hire 2 Driver Relationship Officers; 1 Data Analyst; brief and onboard new hires | Founder / HR | JD 2,400 |
| 17 | Jun 15 – Jun 21 | Marketing | Pre-launch driver recruitment campaign: Facebook, Instagram, WhatsApp groups; mosques, petrol stations | Marketing | JD 3,000 |
| 18 | Jun 22 – Jun 28 | Tech | Apps approved and live on stores (soft, invite-only); backend infrastructure scaled to prod | CTO | JD 1,500 |
| 18 | Jun 22 – Jun 28 | Ops | STAGE GATE 1 REVIEW: Tech sign-off, LTRC licence confirmed, team in place, 50+ drivers waitlisted | Founder | — |
| 19 | Jun 29 – Jul 5 | Driver | M0 cohort onboarding begins: 30 drivers, free trial month; KYC, vehicle inspection, app training | Driver Rel Officers | JD 1,200 |
| 19 | Jun 29 – Jul 5 | Marketing | Boycott tailwind activation: post organic content about Fair Ride model vs Uber/Careem commission | Marketing | JD 1,500 |
| 20 | Jul 6 – Jul 12 | Driver | Driver onboarding sessions (3 group sessions in Amman); distribute branded kits; issue app credentials | Driver Rel Officers | JD 600 |
| 20 | Jul 6 – Jul 12 | Marketing | Press outreach: Jordan Times, Roya TV, 7iber; pitch "Fair Ride" story; briefing document ready | Marketing | JD 800 |
| 21 | Jul 13 – Jul 19 | Driver | Week 3 M0 feedback loop: survey all 30 drivers; identify friction points; deploy app hotfixes | CTO / Driver Rel | JD 2,000 |
| 21 | Jul 13 – Jul 19 | Ops | Soft launch internal ride testing: 20 employee testers using the app; measure dispatch time, ETA | COO | — |
| 22 | Jul 20 – Jul 26 | Driver | Open driver waitlist to general public; target 100 total applications; begin M0 week 4 | Marketing / Ops | JD 1,800 |
| 22 | Jul 20 – Jul 26 | Finance | Month 2 financials close; confirm burn rate; update 12-month runway projection | CFO | — |
| 23 | Jul 27 – Aug 2 | Driver | M0 → M1 conversion: onboard 20 drivers to JD 10/month trial tier; 10 churn expected | Driver Rel Officers | JD 200 |
| 23 | Jul 27 – Aug 2 | Rider | Rider pre-registration campaign: WhatsApp viral loop "Save your seat"; collect 500 pre-signups | Marketing | JD 2,500 |
| 24 | Aug 3 – Aug 9 | Driver | M1 onboarding: 30 new drivers; run parallel sessions; aim for 50+ active M0/M1 drivers | Driver Rel Officers | JD 600 |
| 24 | Aug 3 – Aug 9 | Ops | Activate Wasel Go perk: priority dispatch for subscriber riders tested in parallel | CTO / COO | JD 300 |
| 25 | Aug 10 – Aug 16 | Driver | Safety audit: re-inspect top 20 M0 drivers; certify pass/fail; distribute Wasel window stickers | Ops Manager | JD 400 |
| 25 | Aug 10 – Aug 16 | Marketing | Monthly Fairness Report #1 published: show driver earnings, trip counts, zero commission proof | Marketing / Data | JD 600 |
| 26 | Aug 17 – Aug 23 | Ops | STAGE GATE 2 REVIEW: 80+ active drivers, app stable, press coverage secured, rider pre-signups 500+ | Founder | — |
| 26 | Aug 17 – Aug 23 | Finance | Q1 management accounts; board deck update; confirm Series A data room preparation timeline | CFO | — |
| 27 | Aug 24 – Aug 30 | Launch | SOFT LAUNCH DAY: Limited public access (500 invite codes); PR push; founder interview Roya TV | Founder / Marketing | JD 5,000 |
| 27 | Aug 24 – Aug 30 | Ops | War room setup: 3 ops staff monitoring real-time; 1-hour response SLA active; daily standup 8am | COO | — |
| 28 | Aug 31 – Sep 6 | Tech | Monitor crash rates, API latency, dispatch success rate; deploy any critical patches within 24h | CTO | JD 1,500 |
| 28 | Aug 31 – Sep 6 | Marketing | Referral programme live: "Invite a Friend, Both Get a Month of Wasel Go Free" mechanic | Marketing | JD 3,000 |
| 29 | Sep 7 – Sep 13 | Driver | M1 → M2 conversion push: drivers earning > JD 50 net profit/week offered Standard tier (JD 20/mo) | Driver Rel Officers | JD 400 |
| 29 | Sep 7 – Sep 13 | Ops | Review dispatch algorithm: adjust radius, acceptance rate logic; target 85% dispatch success | CTO / COO | JD 800 |
| 30 | Sep 14 – Sep 20 | Rider | Open Wasel Pass subscriptions (JD 10/month); launch "First Month Free" promotion for early adopters | Marketing | JD 2,000 |
| 30 | Sep 14 – Sep 20 | Finance | Month 3 close: first real revenue recognised; compare actuals vs model; report to investors | CFO | — |
| 31 | Sep 21 – Sep 27 | Marketing | Influencer partnerships: 3 Jordanian micro-influencers (100K+ followers) document first Wasel rides | Marketing | JD 2,500 |
| 31 | Sep 21 – Sep 27 | Tech | v1.1 release: improved ETA accuracy, dark mode, Arabic RTL polish, onboarding flow A/B test | Dev Team | JD 4,000 |
| 32 | Sep 28 – Oct 4 | Driver | Driver Milestone Event: celebrate first 100 active drivers; awards ceremony; media coverage | Ops / Marketing | JD 1,200 |
| 32 | Sep 28 – Oct 4 | Ops | Expand pilot zone: add Jabal Amman, Ras Al Ain, Wadi Seer to service coverage | COO | JD 300 |
| 33 | Oct 5 – Oct 11 | Marketing | Monthly Fairness Report #2; "1,000 rides in North Amman" milestone post; community AMA on Instagram | Marketing | JD 600 |
| 33 | Oct 5 – Oct 11 | Finance | Seed investor update: KPIs vs projections; revise 12-month model; identify capital bridge needs | Founder / CFO | — |
| 34 | Oct 12 – Oct 18 | Tech | v1.2 release: scheduled rides, multi-stop trips, receipt export, improved map rendering | Dev Team | JD 4,000 |
| 34 | Oct 12 – Oct 18 | Ops | SLA audit: review all customer complaints; analyse driver churn reasons; adjust onboarding script | Ops Manager | — |
| 35 | Oct 19 – Oct 25 | Driver | M2 → M3 tier upgrade campaign: top earners offered Plus (JD 35/mo) and Pro (JD 55/mo) tiers | Driver Rel Officers | JD 300 |
| 35 | Oct 19 – Oct 25 | Marketing | Corporate accounts outreach: target 10 SMEs in Abdali / Amman 3rd Circle for employee transport deals | Founder / Marketing | JD 1,500 |
| 36 | Oct 26 – Nov 1 | Ops | STAGE GATE 3 REVIEW: 200+ active drivers, 1,000+ riders, revenue tracking vs model, NPS > 50 | Founder | — |
| 37 | Nov 2 – Nov 8 | Launch | FULL AMMAN LAUNCH: Remove invite gates; open app to all; paid media activation (Google, Meta, TikTok) | Marketing / CTO | JD 8,000 |
| 37 | Nov 2 – Nov 8 | Driver | Aggressive driver recruitment: target 500 total drivers by end of Phase 4; incentive JD 50 sign-on | Driver Rel Officers | JD 5,000 |
| 38 | Nov 9 – Nov 15 | Tech | Scale infrastructure: auto-scaling on AWS; CDN for map tiles; implement circuit breakers | CTO | JD 3,000 |
| 38 | Nov 9 – Nov 15 | Marketing | OOH campaign: 10 billboards in Amman (Mecca St, University St, 7th Circle); bus shelter ads | Marketing | JD 6,000 |
| 39 | Nov 16 – Nov 22 | Rider | Corporate accounts programme launch: Wasel Business tier (JD 25/mo, 50 rides, no surge) | Founder / Ops | JD 1,000 |
| 39 | Nov 16 – Nov 22 | Finance | Month 4 close: target JD 30K+ revenue; prepare bridge financing documents if needed | CFO | — |
| 40 | Nov 23 – Nov 29 | Ops | Airport corridor activation: dedicated Wasel zone at QAI Airport; partner with terminal management | COO | JD 2,000 |
| 40 | Nov 23 – Nov 29 | Marketing | Monthly Fairness Report #3; "10,000 rides" milestone campaign; user testimonial video series | Marketing | JD 1,500 |
| 41 | Nov 30 – Dec 6 | Tech | v1.3 release: Wasel Business portal, scheduled corporate pickups, in-app Arabic support centre | Dev Team | JD 4,000 |
| 41 | Nov 30 – Dec 6 | Driver | Driver welfare programme: partner with Ahli Bank for driver loan product; wellness check-ins | Ops Manager | JD 800 |
| 42 | Dec 7 – Dec 13 | Legal | LTRC licence renewal due diligence; annual report submission; update driver registry | Legal | JD 1,000 |
| 42 | Dec 7 – Dec 13 | Finance | Series A preparation: appoint financial advisor; build data room (12 months actuals + projections) | CFO / Founder | JD 2,000 |
| 43 | Dec 14 – Dec 20 | Marketing | Eid al-Fitr / Christmas / New Year campaign planning; special promotions for holiday travel surge | Marketing | JD 2,000 |
| 43 | Dec 14 – Dec 20 | Ops | Pilot expansion scoping: Zarqa and Irbid market assessment; regulatory requirements mapping | COO | JD 1,200 |
| 44 | Dec 21 – Dec 27 | People | Year-end review cycle; salary benchmarking; hire Q1 roles: 2 more Driver Rel, 1 Finance Analyst | Founder / HR | JD 3,600 |
| 44 | Dec 21 – Dec 27 | Finance | STAGE GATE 4 REVIEW: 400+ drivers, 5,000+ riders, monthly revenue JD 35K+, NPS > 60 | Founder | — |
| 45 | Dec 28 – Jan 3 | Finance | Series A roadshow begins: 15 VC/family office meetings; target close Q2 2027 | Founder / CFO | — |
| 46 | Jan 4 – Jan 10 | Tech | v2.0 planning: Wasel Pool (shared rides), Wasel Ladies (female driver/rider), AI dispatch optimisation | CTO | JD 2,000 |
| 46 | Jan 4 – Jan 10 | Ops | Zarqa soft launch preparation: driver recruitment starts; 20 drivers waitlisted for Zarqa zone | COO | JD 1,500 |
| 47 | Jan 11 – Jan 17 | Marketing | Monthly Fairness Report #4; "50,000 rides" milestone (projected); documentary short film release | Marketing | JD 3,000 |
| 47 | Jan 11 – Jan 17 | Finance | Year-end financial audit; statutory filing; board approval of annual accounts | CFO / Auditor | JD 3,500 |
| 48 | Jan 18 – Jan 24 | Tech | Data platform build: event tracking, cohort analysis, driver/rider LTV dashboards (Metabase) | Data Analyst / CTO | JD 2,500 |
| 48 | Jan 18 – Jan 24 | Ops | Zarqa launch: 20 drivers, invite-only, replicate North Amman soft launch playbook | COO | JD 3,000 |
| 49 | Jan 25 – Jan 31 | Marketing | Ramadan campaign prep (March 2027): high-demand season; special rates, charity tie-in | Marketing | JD 1,500 |
| 49 | Jan 25 – Jan 31 | Finance | Series A investor due diligence support; provide data room access to 3 lead investors | CFO | — |
| 50 | Feb 1 – Feb 7 | Tech | v2.0 Sprint 1: Wasel Pool architecture; dynamic ride-matching algorithm design | CTO / Dev | JD 4,000 |
| 50 | Feb 1 – Feb 7 | Ops | Annual operational review: driver satisfaction survey (100%), NPS benchmarking, cost per driver analysis | COO | — |
| 51 | Feb 8 – Feb 14 | Finance | Q1 2027 budget approval; LTRC renewal payment (JD 100K); update 3-year model for Series A | CFO | JD 100,000 |
| 51 | Feb 8 – Feb 14 | Marketing | Brand refresh assessment: year-1 learnings applied; update campaign messaging for year 2 | Marketing | JD 1,000 |
| 52 | Feb 15 – Feb 21 | Ops | STAGE GATE 5 / YEAR-END REVIEW: KPI dashboard review; Series A readiness; Zarqa stable; 600+ drivers | Founder | — |
| 52 | Feb 15 – Feb 21 | Finance | Shareholder annual meeting; year-1 financials; year-2 strategy presentation | Founder / CFO | — |

# 6. Cost Model & Budget Breakdown

The total Year 1 budget of JD 472,000 is allocated across seven categories. Personnel costs include salaries, benefits, and NSSF contributions at 21.75% employer rate. All figures in Jordanian Dinars (JD).

| Cost Category | P0 | P1 | P2 | P3 | P4 | P5 + Total |
| --- | --- | --- | --- | --- | --- | --- |
| Personnel (salaries + NSSF) | 8,700 | 28,000 | 19,200 | 26,400 | 36,000 | 24,000 / 142,300 |
| Technology (dev + infra) | 1,200 | 42,500 | 2,300 | 12,000 | 8,000 | 8,500 / 74,500 |
| Marketing & Brand | 600 | 7,800 | 6,100 | 14,600 | 19,000 | 5,500 / 53,600 |
| Legal & Regulatory | 3,800 | 2,700 | — | — | 1,500 | — / 8,000 |
| Operations & Driver | — | 1,100 | 2,600 | 3,200 | 10,000 | 4,500 / 21,400 |
| Finance & Professional | 400 | 800 | — | — | 2,000 | 3,500 / 6,700 |
| LTRC Licence Fee | — | — | — | — | — | 100,000 / 100,000 |
| Bank Guarantee | 25,000 | — | — | — | — | — / 25,000 |
| Contingency (5%) | 1,900 | 4,200 | 1,500 | 2,800 | 3,800 | 2,500 / 16,700 |
| TOTAL | 41,600 | 87,100 | 31,700 | 59,000 | 80,300 | 148,500 / JD 472,200 |

PERSONNEL COST DETAIL

| Role | Start Phase | Monthly Salary (JD) | Months (Yr 1) | Annual Cost + NSSF |
| --- | --- | --- | --- | --- |
| Founder (CEO) | P0 | 2,000 | 12 | 29,220 |
| Ops Manager | P0 | 1,000 | 11 | 13,185 |
| Marketing Lead | P0 | 900 | 11 | 11,867 |
| CX Lead | P0 | 700 | 11 | 9,232 |
| CTO / VP Eng | P1 | 2,200 | 9 | 24,030 |
| Driver Rel Officer ×2 | P1 | 700 each | 8 | 13,650 (×2) |
| Data Analyst | P1 | 800 | 8 | 7,788 |
| CX Agent | P3 | 600 | 5 | 3,653 |
| B2B Sales Exec | P3 | 800 | 5 | 4,870 |
| Finance Analyst | P4 | 900 | 3 | 3,285 |
| TOTAL PERSONNEL (incl. NSSF) |  |  |  | JD 120,580 |

# 7. KPI Dashboard Specification

The Wasel KPI dashboard tracks 24 metrics across four categories. All metrics are reported weekly to the founding team and monthly to investors. Dashboard tooling: Google Sheets (Phase 0–2) → Metabase + PostgreSQL (Phase 3+).

CATEGORY 1: GROWTH

| Metric | Phase 3 Target | Phase 4 Target | Phase 5 Target | Definition & Source |
| --- | --- | --- | --- | --- |
| Active Drivers (weekly riders ≥1) | 200 | 400 | 600+ | Admin dashboard, weekly count |
| Registered Riders | 1,000 | 5,000 | 8,000 | App DB, user table |
| Monthly Active Riders (MAR) | 600 | 3,000 | 5,000 | Riders completing ≥1 trip/month |
| Driver MoM Growth Rate | 15% | 20% | 10% | (New drivers / Prior month drivers) |
| Rider MoM Growth Rate | 25% | 28% | 15% | (New riders / Prior month riders) |
| Referral Programme Conversion | 20% | 25% | 20% | Referral invites sent vs codes redeemed |

CATEGORY 2: REVENUE & UNIT ECONOMICS

| Metric | Phase 3 Target | Phase 4 Target | Phase 5 Target | Definition & Source |
| --- | --- | --- | --- | --- |
| Monthly Revenue (JD) | 12,000 | 35,000 | 48,000 | Driver subs + rider subs + corporate |
| Driver Sub Attach Rate | 60% | 70% | 75% | Active drivers paying full tier / total active |
| Rider Sub Attach Rate | 35% | 40% | 42% | Subscriber riders / MAR |
| ARPU — Driver (monthly) | JD 18 | JD 24 | JD 28 | Total driver sub revenue / active drivers |
| ARPU — Rider (monthly) | JD 4.20 | JD 5.50 | JD 6.00 | Total rider sub revenue / MAR |
| Burn Rate (monthly) | < JD 55K | < JD 70K | < JD 80K | Total opex incl. payroll, paid media |
| Cash Runway | > 8 months | > 6 months | > 4 months (Series A expected) | Cash balance / burn rate |

CATEGORY 3: OPERATIONS & QUALITY

| Metric | Phase 3 Target | Phase 4 Target | Phase 5 Target | Definition & Source |
| --- | --- | --- | --- | --- |
| Dispatch Success Rate | 80% | 88% | 92% | Trips matched / requests in zone |
| Average ETA (minutes) | < 8 min | < 6 min | < 5 min | Time from booking to driver arrival |
| Driver Average Rating | ≥ 4.5 / 5 | ≥ 4.6 / 5 | ≥ 4.7 / 5 | Post-trip rider rating, 5-point scale |
| App Crash Rate | < 0.5% | < 0.3% | < 0.2% | Firebase Crashlytics, sessions with crash |
| Driver Monthly Churn | < 12% | < 9% | < 7% | Drivers cancelling sub / active start of month |
| Rider Retention (M+1) | 40% | 50% | 60% | Riders active in month N who ride in N+1 |
| Support SLA (first response) | < 2h | < 1h | < 30 min | WhatsApp Business / in-app ticket |

CATEGORY 4: BRAND & ENGAGEMENT

| Metric | Phase 3 Target | Phase 4 Target | Phase 5 Target | Definition & Source |
| --- | --- | --- | --- | --- |
| Net Promoter Score (NPS) | > 50 | > 60 | > 65 | Post-trip survey, quarterly sample 200+ |
| Instagram Followers | 5,000 | 20,000 | 40,000 | @WaselJO, organic + paid |
| Monthly Fairness Report Views | 500 | 3,000 | 7,000 | Website analytics + LinkedIn reach |
| Press Mentions (monthly) | 2 | 5 | 8 | Media monitor: Jordan Times, Roya, 7iber |
| Corporate Accounts Signed | 0 | 5 | 15 | Signed B2B contracts |

# 8. Risk Register

Likelihood and Impact scored 1–5. Risk Score = Likelihood × Impact. Score ≥ 15 = Critical (red); 8–14 = High (amber); < 8 = Moderate (green). All critical risks require a mitigation plan and named owner.

| ID | Risk | Like. | Impact | Score | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R01 | LTRC licence delayed > 8 weeks | 3 | 5 | 15 | Apply week 2; assign legal priority; prepare regulatory escalation letter; CEO direct liaison with LTRC | Founder / Legal |
| R02 | Seed round not closed by week 8 | 3 | 5 | 15 | Parallel track: 3 angel investors pre-committed; JD 50K bridge from founders; reduce Phase 1 spend by 20% | Founder |
| R03 | Boycott tailwind fades before launch (Week 20) | 3 | 4 | 12 | Accelerate Phase 2 by 2 weeks if sentiment data shows decline; invest in owned content | Marketing |
| R04 | Driver churn > 15%/month in Phase 2 | 3 | 4 | 12 | Weekly earnings transparency report; driver WhatsApp group daily support; extend M1 trial if needed | Driver Rel Officers |
| R05 | App rejected from App Store / Play Store | 2 | 5 | 10 | Early submission (Week 14); dedicated QA pass; maintain TestFlight beta for rapid deployment | CTO |
| R06 | Rider acquisition cost exceeds JD 8/rider | 3 | 3 | 9 | Optimise referral viral loop; shift budget to WhatsApp organic; pause paid media if CAC > JD 10 | Marketing |
| R07 | Uber/Careem response: zero-commission promotion | 2 | 4 | 8 | Position on trust and local ownership, not just price; activate community loyalty programmes | Founder |
| R08 | Cyberattack / data breach | 2 | 4 | 8 | ISO 27001 controls; penetration test before launch; PDPL-compliant DPA; cyber insurance | CTO |
| R09 | Key hire fails (CTO vacancy) | 2 | 4 | 8 | Identify 3 backup candidates; maintain vendor relationship as fallback; consider fractional CTO | Founder |
| R10 | Jordan regulatory tightening (e.g., new LTRC rules) | 2 | 3 | 6 | LTRC relationship management; quarterly regulatory scan; legal counsel on retainer | Legal |
| R11 | Driver income below expectation causing churn | 2 | 3 | 6 | Pre-launch earnings simulator in driver app; 90-day earnings guarantee for first 50 drivers | Ops Manager |
| R12 | FX risk (JD/USD peg) | 1 | 3 | 3 | Jordan maintains USD peg; monitor only. Low probability of regime change | CFO |

# 9. Launch Playbook — Day -14 to Day +14

The soft launch on August 24, 2026 (Day 0) is the most critical operational moment of Year 1. The following playbook governs all activity in the two weeks before and after launch. Every task has a specific owner and pass/fail criterion.

PRE-LAUNCH: DAYS -14 TO -8 (AUG 10–16)

| Day | Activity | Detail | Owner | Pass Criterion |
| --- | --- | --- | --- | --- |
| D-14 | Infrastructure stress test | Simulate 500 concurrent users; 1,000 trip requests/hr; check auto-scaling triggers | CTO | Zero downtime, p99 < 3s |
| D-13 | Driver final safety check | Re-inspect all 80 active drivers; vehicles, documents, app functionality | Driver Rel | 100% pass rate |
| D-12 | Invite code generation | Generate 500 unique invite codes; test redemption flow end-to-end | CTO / Ops | All 500 codes valid and redeemable |
| D-11 | Press briefings | Brief Jordan Times, Roya TV, 7iber under embargo; provide launch facts sheet | Marketing | 3+ outlets confirmed for Day 0 coverage |
| D-10 | Driver launch briefing session | Full team call (all 80 drivers); launch protocol, support contacts, FAQ | COO / Driver Rel | 90%+ attendance |
| D-8 | Rider invite code distribution | Send codes to 500 pre-registered riders via WhatsApp + email; activation instructions | Marketing / CTO | 200+ codes activated within 48h |

PRE-LAUNCH: DAYS -7 TO -1 (AUG 17–23)

| Day | Activity | Detail | Owner | Pass Criterion |
| --- | --- | --- | --- | --- |
| D-7 | War room setup | Configure monitoring: Grafana dashboards, PagerDuty alerts, Slack ops channel with CTO + COO | CTO | All alerts firing correctly |
| D-6 | Social media pre-launch teaser | Post "Something fair is coming to Amman" countdown content on Instagram, Facebook, TikTok | Marketing | 500+ engagements |
| D-5 | Payment system final test | End-to-end CliQ payment: 20 test transactions; refund flow; subscription billing cycle | CTO | Zero failed transactions |
| D-3 | Founder media interview | Pre-record Roya TV segment; record Instagram Live; finalise key messages for launch day | Founder / Marketing | Segment confirmed for Day 0 |
| D-2 | Support team readiness drill | Simulate 50 concurrent support tickets; WhatsApp Business queue; measure response time | CX Lead | < 30 min avg response in drill |
| D-1 | GO / NO-GO decision | Full team review checklist: tech ✓, drivers ✓, legal ✓, cash ✓, media ✓. CEO final sign-off | Founder | All 5 criteria met |

LAUNCH DAY (DAY 0: AUGUST 24, 2026)

| 06:00 AM | Open Wasel app to all 500 invite-code holders (all cities, North Amman zone active) |
| --- | --- |
| 07:00 AM | CEO Instagram Live: "Wasel is live. Fair rides start now." — 30 minute Q&A session |
| 08:00 AM | Roya TV segment airs (pre-recorded interview with Wasel founder) |
| 09:00 AM | First 100 trips milestone monitoring — war room tracking dispatch rate |
| 12:00 PM | Jordan Times article published; 7iber piece live; share across all social channels |
| 16:00 PM | First daily debrief: crash rate, ETA, dispatch success, customer complaints reviewed |
| 18:00 PM | Driver celebratory WhatsApp message: trip count, earnings update, "thank you" from CEO |
| 21:00 PM | End-of-day report to seed investors: Day 1 metrics, media coverage roundup |

POST-LAUNCH: DAYS +1 TO +14 (AUG 25 – SEP 6)

| Day | Activity | Detail | Owner | Pass Criterion |
| --- | --- | --- | --- | --- |
| D+1 | Patch deployment window | Any P0 bugs found Day 0 fixed and deployed by noon; no new features until D+3 | CTO | Zero P0 bugs outstanding |
| D+2 | Rider experience survey | In-app survey to all Day 0 riders (20 questions); target 100 responses | CX Lead | 100 responses, NPS > 40 |
| D+3 | Referral programme launch | "Invite a Friend, Both Get Wasel Go Free for 1 Month" — automated WhatsApp link share | Marketing / CTO | 200+ referral links shared |
| D+5 | Press follow-up | Send Day 1–5 metric press release to all media contacts; pitch "1,000 rides" milestone | Marketing | 1 follow-up article published |
| D+7 | Week 1 metrics review | Full team review: dispatch rate, churn, top complaints, driver satisfaction, revenue pace | Founder | Decision: scale or remediate |
| D+10 | Wasel Pass open | Open Wasel Pass (JD 10/mo) subscriptions; "First Month Free" for first 200 sign-ups | Marketing / CTO | 100+ Pass sign-ups in 72h |
| D+14 | Two-week performance review | Board deck update: actuals vs plan; cash burn vs forecast; invite code expansion decision | Founder / CFO | Board approval to expand to 2,000 codes |

# 10. Final Deliverables Checklist

The following checklist tracks all major legal, technical, operational, and commercial deliverables required before and during Year 1. Each item has an owner, target week, and current status column to be maintained in real time.

LEGAL & REGULATORY

| Deliverable | Owner | Target Week | Phase | Status |
| --- | --- | --- | --- | --- |
| Company incorporated (Jordan) | Legal / Founder | Wk 1 | P0 | [ ] |
| Corporate bank account opened | CFO | Wk 1 | P0 | [ ] |
| LTRC licence application filed | Legal | Wk 2 | P0 | [ ] |
| Bank guarantee (JD 25K) lodged | CFO | Wk 2 | P0 | [ ] |
| Driver T&Cs + rider T&Cs finalised | Legal | Wk 3 | P0 | [ ] |
| PDPL data protection registration | Legal | Wk 3 | P0 | [ ] |
| LTRC licence received | Legal | Wk 12 | P1 | [ ] |
| Insurance policy live (fleet + liability) | Legal / COO | Wk 12 | P1 | [ ] |
| LTRC annual renewal + JD 100K fee | Legal / CFO | Wk 51 | P5 | [ ] |

TECHNOLOGY

| Deliverable | Owner | Target Week | Phase | Status |
| --- | --- | --- | --- | --- |
| Development contract signed | CTO | Wk 5 | P0 | [ ] |
| Driver app — core flow (Sprints 1–3) | Dev Team | Wk 10 | P1 | [ ] |
| Rider app — core flow (Sprint 3) | Dev Team | Wk 10 | P1 | [ ] |
| Payment integration live (CliQ + Visa) | Dev Team | Wk 10 | P1 | [ ] |
| Admin dashboard (KYC, subs, analytics) | Dev Team | Wk 11 | P1 | [ ] |
| iOS App Store approval | CTO | Wk 18 | P1 | [ ] |
| Google Play Store approval | CTO | Wk 18 | P1 | [ ] |
| v1.1 release (ETA, dark mode, Arabic) | Dev Team | Wk 31 | P3 | [ ] |
| v1.2 release (scheduled rides, multi-stop) | Dev Team | Wk 34 | P3 | [ ] |
| AWS auto-scaling live (Phase 4) | CTO | Wk 38 | P4 | [ ] |
| v1.3 release (Wasel Business portal) | Dev Team | Wk 41 | P4 | [ ] |
| Metabase data platform live | Data Analyst | Wk 48 | P5 | [ ] |

COMMERCIAL & MARKETING

| Deliverable | Owner | Target Week | Phase | Status |
| --- | --- | --- | --- | --- |
| Visual identity (logo, Arabic/EN type) | Marketing | Wk 7 | P1 | [ ] |
| Driver waitlist landing page live | Marketing / CTO | Wk 8 | P1 | [ ] |
| Branded driver kits ordered (merch, decals) | Marketing | Wk 14 | P1 | [ ] |
| Monthly Fairness Report #1 published | Marketing / Data | Wk 25 | P2 | [ ] |
| Soft launch: 500 invite codes sent | Marketing / CTO | Wk 27 | P3 | [ ] |
| Wasel Pass subscriptions open | Marketing | Wk 30 | P3 | [ ] |
| OOH campaign live (10 Amman billboards) | Marketing | Wk 38 | P4 | [ ] |
| Wasel Business corporate tier launched | Founder / Ops | Wk 39 | P4 | [ ] |
| Airport corridor (QAI) activated | COO | Wk 40 | P4 | [ ] |
| Series A data room ready | CFO / Founder | Wk 42 | P4 | [ ] |
| Zarqa soft launch | COO | Wk 48 | P5 | [ ] |
| Series A roadshow launched (15 meetings) | Founder | Wk 45 | P5 | [ ] |
| Year-end shareholder meeting | Founder / CFO | Wk 52 | P5 | [ ] |

# 11. Appendix: Notes & Definitions

DRIVER COHORT DEFINITIONS

| M0 (Trial) | Free trial month. New drivers onboarded at zero cost. Designed to de-risk the switch from Uber/Careem. Target: 100% app activation within 48h of onboarding. |
| --- | --- |
| M1 (Ramp) | Month 2. Reduced subscription fee of JD 10/month. Driver has proven the platform; Wasel has confirmed compliance and quality. Target: 60% of M0 convert. |
| M2 (Active) | Month 3+. Full subscription tier activated: Standard (JD 20/mo), Plus (JD 35/mo), or Pro (JD 55/mo) based on trip capacity and earnings history. |
| M3 (Champion) | Drivers in M2 for 3+ months with rating ≥ 4.7, churn risk low. Eligible for Wasel Champion programme: featured in Fairness Reports, referral bonuses. |

RIDER TIER DEFINITIONS

| Free (Base) | No subscription. Pay per trip at JD 2.37 standard fare. No surge cap, standard dispatch priority. |
| --- | --- |
| Wasel Go | JD 5/month. Perks: priority dispatch (queue jump), surge protection (capped at 1.3× base), 1 free cancellation per day. No fare discount. |
| Wasel Pass | JD 10/month. All Wasel Go perks + 1 free ride/month (up to JD 5 value), airport priority lane, business receipt export. No ongoing fare discount. |
| Wasel Business | JD 25/month (corporate account). Up to 50 rides/month, central billing, no surge, dedicated account manager. |

GLOSSARY

| ARPU | Average Revenue Per User (driver or rider) |
| --- | --- |
| CAC | Customer Acquisition Cost |
| CliQ | Jordan's instant bank-to-bank payment system |
| DXA | Dexa units (document measurement, 1440 DXA = 1 inch) |
| JD | Jordanian Dinar (pegged at 1 JD = $1.41 USD) |
| LTRC | Land Transport Regulatory Commission — the Jordanian authority that licences ride-hailing operators |
| LTV | Lifetime Value of a customer |
| MAR | Monthly Active Riders |
| MoM | Month-over-Month |
| NPS | Net Promoter Score (−100 to +100; > 50 is excellent) |
| NSSF | National Social Security Fund — Jordan employer contribution at 21.75% |
| PDPL | Personal Data Protection Law — Jordan's data privacy regulation |
| P0–P5 | Execution phases 0–5 of the Wasel Year 1 roadmap |
| QAI | Queen Alia International Airport, Amman |
| SLA | Service Level Agreement |
| SOS | Emergency safety button in-app for rider/driver incident reporting |

WASEL

"To move Jordan forward — fairly."

Year 1 Execution Plan · February 2026 – February 2027

Version 1.0 · Confidential