## Cover
WASEL
Year 1 Execution Timeline · Gantt Chart & Budget
February 2026 – February 2027
"To move Jordan forward — fairly."
CONFIDENTIAL – For Internal & Investor Use Only
Sheets in this workbook:
| TABLE 1 — Gantt Dataset | All 80+ tasks with dates, workstream, owner, budget, phase
| TABLE 2 — Gantt Visual | Week-column Gantt grid; colour-coded by phase
| Budget | Phased cost model by category + total
| KPI Dashboard | All 24 KPIs with phase targets and definitions

## TABLE 1 — Gantt Dataset
ID | Phase | Start Week | End Week | Workstream | Task / Deliverable | Owner | Budget (JD) | Milestone? | Start Date | End Date | Duration (wks)
1 | P0 | 1 | 1 | Legal | Incorporate company; appoint counsel; open bank account | Founder/Legal | 500 |  | 23 Feb 2026 | 01 Mar 2026 | 1
2 | P0 | 1 | 1 | Finance | Draft fundraising materials; update investor deck | Founder/CFO |  |  | 23 Feb 2026 | 01 Mar 2026 | 1
3 | P0 | 2 | 2 | Legal | File LTRC operator licence application; JD 25K bank guarantee | Legal | 2500 | YES | 02 Mar 2026 | 08 Mar 2026 | 1
4 | P0 | 2 | 3 | Finance | Launch seed round roadshow; first LP meetings | Founder |  |  | 02 Mar 2026 | 15 Mar 2026 | 2
5 | P0 | 3 | 3 | Legal | PDPL registration; draft driver & rider T&Cs | Legal | 300 |  | 09 Mar 2026 | 15 Mar 2026 | 1
6 | P0 | 3 | 3 | Ops | Define Amman pilot zone boundaries (North Amman) | COO |  |  | 09 Mar 2026 | 15 Mar 2026 | 1
7 | P0 | 4 | 4 | Tech | Issue RFPs for app development; select vendor | CTO |  |  | 16 Mar 2026 | 22 Mar 2026 | 1
8 | P0 | 4 | 4 | Legal | Finalise employment contracts for founding team | HR/Legal |  |  | 16 Mar 2026 | 22 Mar 2026 | 1
9 | P0 | 5 | 5 | Finance | Close seed round; wire funds; set financial reporting cadence | CFO/Founder |  | YES | 23 Mar 2026 | 29 Mar 2026 | 1
10 | P0 | 5 | 5 | Tech | Sign dev contract; kick off sprint planning; set up tools | CTO | 1200 |  | 23 Mar 2026 | 29 Mar 2026 | 1
11 | P0 | 6 | 6 | Legal | LTRC follow-up; register vehicles list | Legal | 500 |  | 30 Mar 2026 | 05 Apr 2026 | 1
12 | P0 | 6 | 6 | People | Hire: Ops Manager, CX Lead, Marketing Lead (3 FTE) | Founder | 3600 |  | 30 Mar 2026 | 05 Apr 2026 | 1
13 | P1 | 7 | 7 | Tech | Sprint 1: Architecture, auth, user registration, map SDK | CTO/Dev | 4000 |  | 06 Apr 2026 | 12 Apr 2026 | 1
14 | P1 | 7 | 7 | Brand | Finalise visual identity: logo, Arabic/EN typography | Marketing | 1500 |  | 06 Apr 2026 | 12 Apr 2026 | 1
15 | P1 | 8 | 8 | Tech | Sprint 2: Driver app core flow; subscription billing module | Dev Team | 4000 |  | 13 Apr 2026 | 19 Apr 2026 | 1
16 | P1 | 8 | 8 | Marketing | Driver waitlist landing page; launch @WaselJO social media | Marketing | 600 |  | 13 Apr 2026 | 19 Apr 2026 | 1
17 | P1 | 9 | 9 | Tech | Sprint 3: Rider app, real-time tracking, payment integration | Dev Team | 4000 |  | 20 Apr 2026 | 26 Apr 2026 | 1
18 | P1 | 9 | 9 | Ops | Map Amman zones; define service hours; draft driver SOPs | COO | 400 |  | 20 Apr 2026 | 26 Apr 2026 | 1
19 | P1 | 10 | 10 | Tech | Sprint 4: Admin dashboard; KYC, analytics, notifications | Dev Team | 4000 |  | 27 Apr 2026 | 03 May 2026 | 1
20 | P1 | 10 | 10 | Marketing | Driver acquisition campaign brief; testimonial concept | Marketing | 800 |  | 27 Apr 2026 | 03 May 2026 | 1
21 | P1 | 11 | 11 | Tech | Sprint 5: Ratings, in-app chat, SOS button, accessibility | Dev Team | 4000 |  | 04 May 2026 | 10 May 2026 | 1
22 | P1 | 11 | 11 | Finance | Set up accounting (QuickBooks); payroll; reporting template | CFO | 400 |  | 04 May 2026 | 10 May 2026 | 1
23 | P1 | 12 | 12 | Tech | Sprint 6: Surge cap logic; Wasel Pass/Go perk engine | Dev Team | 4000 |  | 11 May 2026 | 17 May 2026 | 1
24 | P1 | 12 | 12 | Legal | LTRC licence received (expected); sign insurance policy | Legal | 2200 | YES | 11 May 2026 | 17 May 2026 | 1
25 | P1 | 13 | 13 | Tech | Sprint 7: Full integration + load testing (500 concurrent) | Dev/QA | 4000 |  | 18 May 2026 | 24 May 2026 | 1
26 | P1 | 13 | 13 | Ops | Driver vehicle inspection protocol; partner with 2 garages | COO | 800 |  | 18 May 2026 | 24 May 2026 | 1
27 | P1 | 14 | 14 | Tech | Sprint 8: iOS App Store + Google Play submission | CTO | 4000 | YES | 25 May 2026 | 31 May 2026 | 1
28 | P1 | 14 | 14 | Marketing | Branded merch design; order print run (decals, kits) | Marketing | 2400 |  | 25 May 2026 | 31 May 2026 | 1
29 | P1 | 15 | 15 | Tech | Sprint 9: App Store review cycle; prepare v1.0 release candidate | Dev/CTO | 4000 |  | 01 Jun 2026 | 07 Jun 2026 | 1
30 | P1 | 15 | 15 | Ops | Define driver support SLA; set up WhatsApp Business helpline | Ops Mgr | 300 |  | 01 Jun 2026 | 07 Jun 2026 | 1
31 | P1 | 16 | 16 | Tech | Sprint 10: Final UAT with 10 testers; fix P0/P1 bugs; tag v1.0 | QA/Dev | 4000 |  | 08 Jun 2026 | 14 Jun 2026 | 1
32 | P1 | 16 | 16 | Finance | Board update; investor report #1; cash flow vs budget | CFO |  |  | 08 Jun 2026 | 14 Jun 2026 | 1
33 | P1 | 17 | 17 | People | Hire: CTO (or VP Eng), 2 Driver Rel Officers, 1 Data Analyst | Founder/HR | 2400 |  | 15 Jun 2026 | 21 Jun 2026 | 1
34 | P1 | 17 | 17 | Marketing | Pre-launch driver recruitment: Facebook, WhatsApp, petrol stns | Marketing | 3000 |  | 15 Jun 2026 | 21 Jun 2026 | 1
35 | P1 | 18 | 18 | Tech | Apps approved & live on stores (invite-only); prod infra scaled | CTO | 1500 | YES | 22 Jun 2026 | 28 Jun 2026 | 1
36 | P1 | 18 | 18 | Ops | STAGE GATE 1 REVIEW: Tech OK, LTRC confirmed, 50+ waitlist | Founder |  | YES | 22 Jun 2026 | 28 Jun 2026 | 1
37 | P2 | 19 | 19 | Driver | M0 cohort begins: 30 drivers, free trial, KYC, training | Driver Rel | 1200 |  | 29 Jun 2026 | 05 Jul 2026 | 1
38 | P2 | 19 | 19 | Marketing | Boycott tailwind activation: Fair Ride organic content | Marketing | 1500 |  | 29 Jun 2026 | 05 Jul 2026 | 1
39 | P2 | 20 | 20 | Driver | Driver onboarding sessions (3 group sessions); distribute kits | Driver Rel | 600 |  | 06 Jul 2026 | 12 Jul 2026 | 1
40 | P2 | 20 | 20 | Marketing | Press outreach: Jordan Times, Roya TV, 7iber | Marketing | 800 |  | 06 Jul 2026 | 12 Jul 2026 | 1
41 | P2 | 21 | 21 | Driver | Week 3 M0 feedback loop; survey all drivers; app hotfixes | CTO/Driver Rel | 2000 |  | 13 Jul 2026 | 19 Jul 2026 | 1
42 | P2 | 21 | 21 | Ops | Internal ride testing: 20 employee testers; measure dispatch | COO |  |  | 13 Jul 2026 | 19 Jul 2026 | 1
43 | P2 | 22 | 22 | Driver | Open driver waitlist to public; target 100 total applications | Marketing/Ops | 1800 |  | 20 Jul 2026 | 26 Jul 2026 | 1
44 | P2 | 22 | 22 | Finance | Month 2 financials close; confirm burn rate; update runway | CFO |  |  | 20 Jul 2026 | 26 Jul 2026 | 1
45 | P2 | 23 | 23 | Driver | M0→M1 conversion: 20 drivers to JD 10/mo ramp tier | Driver Rel | 200 |  | 27 Jul 2026 | 02 Aug 2026 | 1
46 | P2 | 23 | 23 | Rider | Rider pre-registration: "Save your seat" viral loop; 500 signups | Marketing | 2500 |  | 27 Jul 2026 | 02 Aug 2026 | 1
47 | P2 | 24 | 24 | Driver | M1 onboarding: 30 new drivers; target 50+ active M0/M1 | Driver Rel | 600 |  | 03 Aug 2026 | 09 Aug 2026 | 1
48 | P2 | 24 | 24 | Ops | Activate Wasel Go perk: priority dispatch tested | CTO/COO | 300 |  | 03 Aug 2026 | 09 Aug 2026 | 1
49 | P2 | 25 | 25 | Driver | Safety audit: re-inspect top 20 M0 drivers; certify pass/fail | Ops Mgr | 400 |  | 10 Aug 2026 | 16 Aug 2026 | 1
50 | P2 | 25 | 25 | Marketing | Monthly Fairness Report #1 published | Marketing/Data | 600 | YES | 10 Aug 2026 | 16 Aug 2026 | 1
51 | P2 | 26 | 26 | Ops | STAGE GATE 2: 80+ drivers, stable app, media coverage, 500+ pre-signups | Founder |  | YES | 17 Aug 2026 | 23 Aug 2026 | 1
52 | P2 | 26 | 26 | Finance | Q1 mgmt accounts; board deck update; Series A timeline | CFO |  |  | 17 Aug 2026 | 23 Aug 2026 | 1
53 | P3 | 27 | 27 | Launch | SOFT LAUNCH: 500 invite codes; PR push; Roya TV interview | Founder/Marketing | 5000 | YES | 24 Aug 2026 | 30 Aug 2026 | 1
54 | P3 | 27 | 27 | Ops | War room: 3 ops staff monitoring; 1h SLA active; daily standup | COO |  |  | 24 Aug 2026 | 30 Aug 2026 | 1
55 | P3 | 28 | 28 | Tech | Monitor crash rates, latency, dispatch; deploy patches 24h | CTO | 1500 |  | 31 Aug 2026 | 06 Sep 2026 | 1
56 | P3 | 28 | 28 | Marketing | Referral programme: Invite Friend, Both Get Wasel Go Free | Marketing | 3000 | YES | 31 Aug 2026 | 06 Sep 2026 | 1
57 | P3 | 29 | 29 | Driver | M1→M2 conversion: drivers earning >JD 50/wk offered Standard | Driver Rel | 400 |  | 07 Sep 2026 | 13 Sep 2026 | 1
58 | P3 | 29 | 29 | Ops | Dispatch algorithm review; adjust radius; target 85% success | CTO/COO | 800 |  | 07 Sep 2026 | 13 Sep 2026 | 1
59 | P3 | 30 | 30 | Rider | Wasel Pass subscriptions open; "First Month Free" promotion | Marketing | 2000 | YES | 14 Sep 2026 | 20 Sep 2026 | 1
60 | P3 | 30 | 30 | Finance | Month 3 close: first real revenue; actuals vs model | CFO |  |  | 14 Sep 2026 | 20 Sep 2026 | 1
61 | P3 | 31 | 31 | Marketing | Influencer partnerships: 3 Jordanian micro-influencers | Marketing | 2500 |  | 21 Sep 2026 | 27 Sep 2026 | 1
62 | P3 | 31 | 31 | Tech | v1.1 release: ETA accuracy, dark mode, Arabic RTL, A/B onboarding | Dev Team | 4000 | YES | 21 Sep 2026 | 27 Sep 2026 | 1
63 | P3 | 32 | 32 | Driver | Driver Milestone Event: celebrate 100 active drivers | Ops/Marketing | 1200 | YES | 28 Sep 2026 | 04 Oct 2026 | 1
64 | P3 | 32 | 32 | Ops | Expand pilot zone: add Jabal Amman, Ras Al Ain, Wadi Seer | COO | 300 |  | 28 Sep 2026 | 04 Oct 2026 | 1
65 | P3 | 33 | 33 | Marketing | Fairness Report #2; "1K rides" milestone; Instagram AMA | Marketing | 600 |  | 05 Oct 2026 | 11 Oct 2026 | 1
66 | P3 | 33 | 33 | Finance | Seed investor update: KPIs vs projections; bridge needs | Founder/CFO |  |  | 05 Oct 2026 | 11 Oct 2026 | 1
67 | P3 | 34 | 34 | Tech | v1.2 release: scheduled rides, multi-stop, receipts | Dev Team | 4000 | YES | 12 Oct 2026 | 18 Oct 2026 | 1
68 | P3 | 34 | 34 | Ops | SLA audit; analyse driver churn reasons; adjust onboarding | Ops Mgr |  |  | 12 Oct 2026 | 18 Oct 2026 | 1
69 | P3 | 35 | 35 | Driver | M2→M3 tier upgrade campaign: Plus/Pro tiers offered | Driver Rel | 300 |  | 19 Oct 2026 | 25 Oct 2026 | 1
70 | P3 | 35 | 35 | Marketing | Corporate accounts outreach: 10 SMEs in Abdali/3rd Circle | Founder/Marketing | 1500 |  | 19 Oct 2026 | 25 Oct 2026 | 1
71 | P3 | 36 | 36 | Ops | STAGE GATE 3: 200+ drivers, 1000+ riders, revenue ✓, NPS>50 | Founder |  | YES | 26 Oct 2026 | 01 Nov 2026 | 1
72 | P4 | 37 | 37 | Launch | FULL AMMAN LAUNCH: Remove invite gates; paid media live | Marketing/CTO | 8000 | YES | 02 Nov 2026 | 08 Nov 2026 | 1
73 | P4 | 37 | 37 | Driver | Aggressive recruitment: target 500 drivers; JD 50 sign-on | Driver Rel | 5000 |  | 02 Nov 2026 | 08 Nov 2026 | 1
74 | P4 | 38 | 38 | Tech | Scale infra: AWS auto-scaling; CDN; circuit breakers | CTO | 3000 |  | 09 Nov 2026 | 15 Nov 2026 | 1
75 | P4 | 38 | 38 | Marketing | OOH: 10 Amman billboards; bus shelter ads | Marketing | 6000 |  | 09 Nov 2026 | 15 Nov 2026 | 1
76 | P4 | 39 | 39 | Rider | Wasel Business tier launch (JD 25/mo, 50 rides, no surge) | Founder/Ops | 1000 | YES | 16 Nov 2026 | 22 Nov 2026 | 1
77 | P4 | 39 | 39 | Finance | Month 4 close: target JD 30K+ revenue | CFO |  |  | 16 Nov 2026 | 22 Nov 2026 | 1
78 | P4 | 40 | 40 | Ops | Airport (QAI) corridor activation; partner terminal mgmt | COO | 2000 | YES | 23 Nov 2026 | 29 Nov 2026 | 1
79 | P4 | 40 | 40 | Marketing | Fairness Report #3; "10K rides" milestone campaign | Marketing | 1500 |  | 23 Nov 2026 | 29 Nov 2026 | 1
80 | P4 | 41 | 41 | Tech | v1.3 release: Wasel Business portal, scheduled corporate | Dev Team | 4000 | YES | 30 Nov 2026 | 06 Dec 2026 | 1
81 | P4 | 41 | 41 | Driver | Driver welfare: Ahli Bank loan product; wellness check-ins | Ops Mgr | 800 |  | 30 Nov 2026 | 06 Dec 2026 | 1
82 | P4 | 42 | 42 | Legal | LTRC licence renewal due diligence; annual report submission | Legal | 1000 |  | 07 Dec 2026 | 13 Dec 2026 | 1
83 | P4 | 42 | 42 | Finance | Series A prep: appoint financial advisor; build data room | CFO/Founder | 2000 | YES | 07 Dec 2026 | 13 Dec 2026 | 1
84 | P4 | 43 | 43 | Marketing | Holiday campaigns: Eid/Christmas/NY; special promotions | Marketing | 2000 |  | 14 Dec 2026 | 20 Dec 2026 | 1
85 | P4 | 43 | 43 | Ops | Expansion scoping: Zarqa & Irbid market assessment | COO | 1200 |  | 14 Dec 2026 | 20 Dec 2026 | 1
86 | P4 | 44 | 44 | People | Year-end review; salary benchmarking; hire Q1 roles | Founder/HR | 3600 |  | 21 Dec 2026 | 27 Dec 2026 | 1
87 | P4 | 44 | 44 | Finance | STAGE GATE 4: 400+ drivers, 5000+ riders, JD 35K/mo, NPS>60 | Founder |  | YES | 21 Dec 2026 | 27 Dec 2026 | 1
88 | P5 | 45 | 52 | Finance | Series A roadshow: 15 VC/FO meetings; target close Q2 2027 | Founder/CFO |  | YES | 28 Dec 2026 | 21 Feb 2027 | 8
89 | P5 | 46 | 46 | Tech | v2.0 planning: Pool, Ladies, AI dispatch optimisation | CTO | 2000 |  | 04 Jan 2027 | 10 Jan 2027 | 1
90 | P5 | 46 | 48 | Ops | Zarqa soft launch preparation: 20 drivers waitlisted | COO | 1500 |  | 04 Jan 2027 | 24 Jan 2027 | 3
91 | P5 | 47 | 47 | Marketing | Fairness Report #4; "50K rides" milestone; documentary film | Marketing | 3000 | YES | 11 Jan 2027 | 17 Jan 2027 | 1
92 | P5 | 47 | 47 | Finance | Year-end audit; statutory filing; board approval | CFO/Auditor | 3500 |  | 11 Jan 2027 | 17 Jan 2027 | 1
93 | P5 | 48 | 48 | Tech | Data platform: Metabase + event tracking + LTV dashboards | Data/CTO | 2500 |  | 18 Jan 2027 | 24 Jan 2027 | 1
94 | P5 | 48 | 48 | Ops | Zarqa launch: 20 drivers, invite-only, replicate playbook | COO | 3000 | YES | 18 Jan 2027 | 24 Jan 2027 | 1
95 | P5 | 49 | 49 | Marketing | Ramadan 2027 campaign prep; special rates; charity tie-in | Marketing | 1500 |  | 25 Jan 2027 | 31 Jan 2027 | 1
96 | P5 | 49 | 49 | Finance | Series A due diligence support; data room access granted | CFO |  |  | 25 Jan 2027 | 31 Jan 2027 | 1
97 | P5 | 50 | 51 | Tech | v2.0 Sprint 1: Wasel Pool architecture; ride-matching algo | CTO/Dev | 4000 |  | 01 Feb 2027 | 14 Feb 2027 | 2
98 | P5 | 50 | 50 | Ops | Annual operational review: driver survey; NPS bench; CAC | COO |  |  | 01 Feb 2027 | 07 Feb 2027 | 1
99 | P5 | 51 | 51 | Finance | Q1 2027 budget; LTRC renewal JD 100K; update 3-yr model | CFO | 100000 | YES | 08 Feb 2027 | 14 Feb 2027 | 1
100 | P5 | 51 | 51 | Marketing | Brand refresh assessment; update Year 2 messaging | Marketing | 1000 |  | 08 Feb 2027 | 14 Feb 2027 | 1
101 | P5 | 52 | 52 | Ops | STAGE GATE 5 / YEAR-END: KPIs, Series A, Zarqa, 600+ drivers | Founder |  | YES | 15 Feb 2027 | 21 Feb 2027 | 1
102 | P5 | 52 | 52 | Finance | Shareholder annual meeting; Year 1 financials; Year 2 strategy | Founder/CFO |  | YES | 15 Feb 2027 | 21 Feb 2027 | 1
|  |  |  | TOTAL YEAR 1 BUDGET |  |  | JD 267,600

## TABLE 2 — Gantt Visual
ID | Phase | Workstream | Task | Owner | W1 TODAY | W2 Mar | W3 Mar | W4 Mar | W5 Mar | W6 Mar | W7 Apr | W8 Apr | W9 Apr | W10 Apr | W11 May | W12 May | W13 May | W14 May | W15 Jun | W16 Jun | W17 Jun | W18 Jun | W19 Jun | W20 Jul | W21 Jul | W22 Jul | W23 Jul | W24 Aug | W25 Aug | W26 Aug | W27 Aug | W28 Aug | W29 Sep | W30 Sep | W31 Sep | W32 Sep | W33 Oct | W34 Oct | W35 Oct | W36 Oct | W37 Nov | W38 Nov | W39 Nov | W40 Nov | W41 Nov | W42 Dec | W43 Dec | W44 Dec | W45 Dec | W46 Jan | W47 Jan | W48 Jan | W49 Jan | W50 Feb | W51 Feb | W52 Feb
1 | P0 | Legal | Incorporate company; appoint counsel; open bank account | Founder/Legal
2 | P0 | Finance | Draft fundraising materials; update investor deck | Founder/CFO | bar: W1 TODAY
3 | P0 | Legal | File LTRC operator licence application; JD 25K bank guarante... ★ | Legal
4 | P0 | Finance | Launch seed round roadshow; first LP meetings | Founder | bar: W2 Mar to W3 Mar
5 | P0 | Legal | PDPL registration; draft driver & rider T&Cs | Legal
6 | P0 | Ops | Define Amman pilot zone boundaries (North Amman) | COO | bar: W3 Mar
7 | P0 | Tech | Issue RFPs for app development; select vendor | CTO
8 | P0 | Legal | Finalise employment contracts for founding team | HR/Legal | bar: W4 Mar
9 | P0 | Finance | Close seed round; wire funds; set financial reporting cadenc... ★ | CFO/Founder
10 | P0 | Tech | Sign dev contract; kick off sprint planning; set up tools | CTO | bar: W5 Mar
11 | P0 | Legal | LTRC follow-up; register vehicles list | Legal
12 | P0 | People | Hire: Ops Manager, CX Lead, Marketing Lead (3 FTE) | Founder | bar: W6 Mar
13 | P1 | Tech | Sprint 1: Architecture, auth, user registration, map SDK | CTO/Dev
14 | P1 | Brand | Finalise visual identity: logo, Arabic/EN typography | Marketing | bar: W7 Apr
15 | P1 | Tech | Sprint 2: Driver app core flow; subscription billing module | Dev Team
16 | P1 | Marketing | Driver waitlist landing page; launch @WaselJO social media | Marketing | bar: W8 Apr
17 | P1 | Tech | Sprint 3: Rider app, real-time tracking, payment integration | Dev Team
18 | P1 | Ops | Map Amman zones; define service hours; draft driver SOPs | COO | bar: W9 Apr
19 | P1 | Tech | Sprint 4: Admin dashboard; KYC, analytics, notifications | Dev Team
20 | P1 | Marketing | Driver acquisition campaign brief; testimonial concept | Marketing | bar: W10 Apr
21 | P1 | Tech | Sprint 5: Ratings, in-app chat, SOS button, accessibility | Dev Team
22 | P1 | Finance | Set up accounting (QuickBooks); payroll; reporting template | CFO | bar: W11 May
23 | P1 | Tech | Sprint 6: Surge cap logic; Wasel Pass/Go perk engine | Dev Team
24 | P1 | Legal | LTRC licence received (expected); sign insurance policy ★ | Legal | bar: W12 May
25 | P1 | Tech | Sprint 7: Full integration + load testing (500 concurrent) | Dev/QA
26 | P1 | Ops | Driver vehicle inspection protocol; partner with 2 garages | COO | bar: W13 May
27 | P1 | Tech | Sprint 8: iOS App Store + Google Play submission ★ | CTO
28 | P1 | Marketing | Branded merch design; order print run (decals, kits) | Marketing | bar: W14 May
29 | P1 | Tech | Sprint 9: App Store review cycle; prepare v1.0 release candi... | Dev/CTO
30 | P1 | Ops | Define driver support SLA; set up WhatsApp Business helpline | Ops Mgr | bar: W15 Jun
31 | P1 | Tech | Sprint 10: Final UAT with 10 testers; fix P0/P1 bugs; tag v1... | QA/Dev
32 | P1 | Finance | Board update; investor report #1; cash flow vs budget | CFO | bar: W16 Jun
33 | P1 | People | Hire: CTO (or VP Eng), 2 Driver Rel Officers, 1 Data Analyst | Founder/HR
34 | P1 | Marketing | Pre-launch driver recruitment: Facebook, WhatsApp, petrol st... | Marketing | bar: W17 Jun
35 | P1 | Tech | Apps approved & live on stores (invite-only); prod infra sca... ★ | CTO
36 | P1 | Ops | STAGE GATE 1 REVIEW: Tech OK, LTRC confirmed, 50+ waitlist ★ | Founder | bar: W18 Jun
37 | P2 | Driver | M0 cohort begins: 30 drivers, free trial, KYC, training | Driver Rel
38 | P2 | Marketing | Boycott tailwind activation: Fair Ride organic content | Marketing | bar: W19 Jun
39 | P2 | Driver | Driver onboarding sessions (3 group sessions); distribute ki... | Driver Rel
40 | P2 | Marketing | Press outreach: Jordan Times, Roya TV, 7iber | Marketing | bar: W20 Jul
41 | P2 | Driver | Week 3 M0 feedback loop; survey all drivers; app hotfixes | CTO/Driver Rel
42 | P2 | Ops | Internal ride testing: 20 employee testers; measure dispatch | COO | bar: W21 Jul
43 | P2 | Driver | Open driver waitlist to public; target 100 total application... | Marketing/Ops
44 | P2 | Finance | Month 2 financials close; confirm burn rate; update runway | CFO | bar: W22 Jul
45 | P2 | Driver | M0→M1 conversion: 20 drivers to JD 10/mo ramp tier | Driver Rel
46 | P2 | Rider | Rider pre-registration: "Save your seat" viral loop; 500 sig... | Marketing | bar: W23 Jul
47 | P2 | Driver | M1 onboarding: 30 new drivers; target 50+ active M0/M1 | Driver Rel
48 | P2 | Ops | Activate Wasel Go perk: priority dispatch tested | CTO/COO | bar: W24 Aug
49 | P2 | Driver | Safety audit: re-inspect top 20 M0 drivers; certify pass/fai... | Ops Mgr
50 | P2 | Marketing | Monthly Fairness Report #1 published ★ | Marketing/Data | bar: W25 Aug
51 | P2 | Ops | STAGE GATE 2: 80+ drivers, stable app, media coverage, 500+ ... ★ | Founder
52 | P2 | Finance | Q1 mgmt accounts; board deck update; Series A timeline | CFO | bar: W26 Aug
53 | P3 | Launch | SOFT LAUNCH: 500 invite codes; PR push; Roya TV interview ★ | Founder/Marketing
54 | P3 | Ops | War room: 3 ops staff monitoring; 1h SLA active; daily stand... | COO | bar: W27 Aug
55 | P3 | Tech | Monitor crash rates, latency, dispatch; deploy patches 24h | CTO
56 | P3 | Marketing | Referral programme: Invite Friend, Both Get Wasel Go Free ★ | Marketing | bar: W28 Aug
57 | P3 | Driver | M1→M2 conversion: drivers earning >JD 50/wk offered Standard | Driver Rel
58 | P3 | Ops | Dispatch algorithm review; adjust radius; target 85% success | CTO/COO | bar: W29 Sep
59 | P3 | Rider | Wasel Pass subscriptions open; "First Month Free" promotion ★ | Marketing
60 | P3 | Finance | Month 3 close: first real revenue; actuals vs model | CFO | bar: W30 Sep
61 | P3 | Marketing | Influencer partnerships: 3 Jordanian micro-influencers | Marketing
62 | P3 | Tech | v1.1 release: ETA accuracy, dark mode, Arabic RTL, A/B onboa... ★ | Dev Team | bar: W31 Sep
63 | P3 | Driver | Driver Milestone Event: celebrate 100 active drivers ★ | Ops/Marketing
64 | P3 | Ops | Expand pilot zone: add Jabal Amman, Ras Al Ain, Wadi Seer | COO | bar: W32 Sep
65 | P3 | Marketing | Fairness Report #2; "1K rides" milestone; Instagram AMA | Marketing
66 | P3 | Finance | Seed investor update: KPIs vs projections; bridge needs | Founder/CFO | bar: W33 Oct
67 | P3 | Tech | v1.2 release: scheduled rides, multi-stop, receipts ★ | Dev Team
68 | P3 | Ops | SLA audit; analyse driver churn reasons; adjust onboarding | Ops Mgr | bar: W34 Oct
69 | P3 | Driver | M2→M3 tier upgrade campaign: Plus/Pro tiers offered | Driver Rel
70 | P3 | Marketing | Corporate accounts outreach: 10 SMEs in Abdali/3rd Circle | Founder/Marketing | bar: W35 Oct
71 | P3 | Ops | STAGE GATE 3: 200+ drivers, 1000+ riders, revenue ✓, NPS>50 ★ | Founder
72 | P4 | Launch | FULL AMMAN LAUNCH: Remove invite gates; paid media live ★ | Marketing/CTO | bar: W37 Nov
73 | P4 | Driver | Aggressive recruitment: target 500 drivers; JD 50 sign-on | Driver Rel
74 | P4 | Tech | Scale infra: AWS auto-scaling; CDN; circuit breakers | CTO | bar: W38 Nov
75 | P4 | Marketing | OOH: 10 Amman billboards; bus shelter ads | Marketing
76 | P4 | Rider | Wasel Business tier launch (JD 25/mo, 50 rides, no surge) ★ | Founder/Ops | bar: W39 Nov
77 | P4 | Finance | Month 4 close: target JD 30K+ revenue | CFO
78 | P4 | Ops | Airport (QAI) corridor activation; partner terminal mgmt ★ | COO | bar: W40 Nov
79 | P4 | Marketing | Fairness Report #3; "10K rides" milestone campaign | Marketing
80 | P4 | Tech | v1.3 release: Wasel Business portal, scheduled corporate ★ | Dev Team | bar: W41 Nov
81 | P4 | Driver | Driver welfare: Ahli Bank loan product; wellness check-ins | Ops Mgr
82 | P4 | Legal | LTRC licence renewal due diligence; annual report submission | Legal | bar: W42 Dec
83 | P4 | Finance | Series A prep: appoint financial advisor; build data room ★ | CFO/Founder
84 | P4 | Marketing | Holiday campaigns: Eid/Christmas/NY; special promotions | Marketing | bar: W43 Dec
85 | P4 | Ops | Expansion scoping: Zarqa & Irbid market assessment | COO
86 | P4 | People | Year-end review; salary benchmarking; hire Q1 roles | Founder/HR | bar: W44 Dec
87 | P4 | Finance | STAGE GATE 4: 400+ drivers, 5000+ riders, JD 35K/mo, NPS>60 ★ | Founder
88 | P5 | Finance | Series A roadshow: 15 VC/FO meetings; target close Q2 2027 ★ | Founder/CFO | bar: W45 Dec to W52 Feb
89 | P5 | Tech | v2.0 planning: Pool, Ladies, AI dispatch optimisation | CTO
90 | P5 | Ops | Zarqa soft launch preparation: 20 drivers waitlisted | COO | bar: W46 Jan to W48 Jan
91 | P5 | Marketing | Fairness Report #4; "50K rides" milestone; documentary film ★ | Marketing
92 | P5 | Finance | Year-end audit; statutory filing; board approval | CFO/Auditor | bar: W47 Jan
93 | P5 | Tech | Data platform: Metabase + event tracking + LTV dashboards | Data/CTO
94 | P5 | Ops | Zarqa launch: 20 drivers, invite-only, replicate playbook ★ | COO | bar: W48 Jan
95 | P5 | Marketing | Ramadan 2027 campaign prep; special rates; charity tie-in | Marketing
96 | P5 | Finance | Series A due diligence support; data room access granted | CFO | bar: W49 Jan
97 | P5 | Tech | v2.0 Sprint 1: Wasel Pool architecture; ride-matching algo | CTO/Dev
98 | P5 | Ops | Annual operational review: driver survey; NPS bench; CAC | COO | bar: W50 Feb
99 | P5 | Finance | Q1 2027 budget; LTRC renewal JD 100K; update 3-yr model ★ | CFO
100 | P5 | Marketing | Brand refresh assessment; update Year 2 messaging | Marketing | bar: W51 Feb
101 | P5 | Ops | STAGE GATE 5 / YEAR-END: KPIs, Series A, Zarqa, 600+ drivers ★ | Founder
102 | P5 | Finance | Shareholder annual meeting; Year 1 financials; Year 2 strate... ★ | Founder/CFO | bar: W52 Feb

## Budget
WASEL — Year 1 Costed Budget Breakdown (JD)
Cost Category | P0 (Wks 1-6) | P1 (Wks 7-18) | P2 (Wks 19-26) | P3 (Wks 27-36) | P4 (Wks 37-44) | P5 (Wks 45-52) | TOTAL (JD) | % of Total
Personnel (salaries + NSSF 21.75%) | JD 8,700 | JD 28,000 | JD 19,200 | JD 26,400 | JD 36,000 | JD 24,000 | JD 142,300 | 31.75%
Technology (development + infra) | JD 1,200 | JD 42,500 | JD 2,300 | JD 12,000 | JD 8,000 | JD 8,500 | JD 74,500 | 16.62%
Marketing & Brand | JD 600 | JD 7,800 | JD 6,100 | JD 14,600 | JD 19,000 | JD 5,500 | JD 53,600 | 11.96%
Legal & Regulatory | JD 3,800 | JD 2,700 | — | — | JD 1,500 | — | JD 8,000 | 1.785%
Operations & Driver Acquisition | — | JD 1,100 | JD 2,600 | JD 3,200 | JD 10,000 | JD 4,500 | JD 21,400 | 4.775%
Finance & Professional Services | JD 400 | JD 800 | — | — | JD 2,000 | JD 3,500 | JD 6,700 | 1.495%
LTRC Annual Licence Fee | — | — | — | — | — | JD 100,000 | JD 100,000 | 22.31%
Bank Guarantee (JD 25K) | JD 25,000 | — | — | — | — | — | JD 25,000 | 5.578%
Contingency (5% of direct costs) | JD 1,900 | JD 4,200 | JD 1,500 | JD 2,800 | JD 3,800 | JD 2,500 | JD 16,700 | 3.726%
GRAND TOTAL | JD 41,600 | JD 87,100 | JD 31,700 | JD 59,000 | JD 80,300 | JD 148,500 | JD 448,200 | 100%
Year 1 Revenue & P&L Summary
Driver Subscription Revenue | JD 154,000 |  | Monthly fee × active drivers × 12 months (blended tier)
Rider Subscription Revenue | JD 130,000 |  | Wasel Go + Wasel Pass + Wasel Business accounts
TOTAL REVENUE (Year 1) | JD 284,000 |  | Excludes trip fare revenue (Wasel does not take commission)
Total Operating Costs | JD 448,200 |  | Per budget above
Net Operating Loss (Year 1) | JD (164,200) |  | Revenue minus total costs
Seed Raise Target | JD 472,000 |  | ~$665,000 USD at 1 JD = $1.41
Implied Runway | ~14 months |  | From seed close to Series A gate (Stage Gate 5)

## KPI Dashboard
WASEL — KPI Dashboard Specification
# | Category | Metric | P3 Target | P4 Target | P5 Target | Definition | Source / Tool
1 | Growth | Active Drivers (≥1 trip/week) | 200 | 400 | 600+ | Drivers completing ≥1 trip in 7-day window | Admin dashboard
2 | Growth | Registered Riders | 1,000 | 5,000 | 8,000 | Total user accounts created in rider app | App DB
3 | Growth | Monthly Active Riders (MAR) | 600 | 3,000 | 5,000 | Riders completing ≥1 trip in calendar month | App DB
4 | Growth | Driver MoM Growth Rate | 15% | 20% | 10% | (New drivers / Prior month total drivers) − 1 | Admin dashboard
5 | Growth | Rider MoM Growth Rate | 25% | 28% | 15% | (New riders / Prior month total riders) − 1 | App DB
6 | Growth | Referral Conversion Rate | 20% | 25% | 20% | Referral codes redeemed / invites sent | Marketing analytics
7 | Revenue | Monthly Revenue (JD) | 12,000 | 35,000 | 48,000 | Driver + rider subscriptions + corporate accounts | QuickBooks / Stripe
8 | Revenue | Driver Sub Attach Rate | 60% | 70% | 75% | Active paying drivers / total active drivers | Admin dashboard
9 | Revenue | Rider Sub Attach Rate | 35% | 40% | 42% | Subscriber riders / Monthly Active Riders | App DB
10 | Revenue | ARPU — Driver (monthly) | JD 18 | JD 24 | JD 28 | Driver sub revenue / active drivers | QuickBooks
11 | Revenue | ARPU — Rider (monthly) | JD 4.20 | JD 5.50 | JD 6.00 | Rider sub revenue / MAR | QuickBooks
12 | Revenue | Monthly Burn Rate | <JD 55K | <JD 70K | <JD 80K | Total operating expenses in calendar month | QuickBooks
13 | Revenue | Cash Runway (months) | >8 | >6 | >4 | Cash balance / monthly burn rate | CFO dashboard
14 | Ops | Dispatch Success Rate | 80% | 88% | 92% | Matched trips / total trip requests in zone | Backend analytics
15 | Ops | Average ETA (minutes) | <8 min | <6 min | <5 min | Time: booking confirmed → driver arrives | App telemetry
16 | Ops | Driver Average Rating | ≥4.5 | ≥4.6 | ≥4.7 | Post-trip rider rating, 5-point scale | App DB
17 | Ops | App Crash Rate | <0.5% | <0.3% | <0.2% | Sessions with crash / total sessions | Firebase Crashlytics
18 | Ops | Driver Monthly Churn | <12% | <9% | <7% | Cancellations / active drivers at start of month | Admin dashboard
19 | Ops | Rider Retention (M+1) | 40% | 50% | 60% | Riders active in month N who ride again in N+1 | Cohort analysis, Metabase
20 | Ops | Support SLA — First Response | <2h | <1h | <30 min | Time from ticket created to first agent response | WhatsApp Business / Zendesk
21 | Brand | Net Promoter Score (NPS) | >50 | >60 | >65 | Post-trip survey, quarterly sample ≥200 riders | In-app survey
22 | Brand | Instagram Followers (@WaselJO) | 5,000 | 20,000 | 40,000 | Organic + paid; tracked via Instagram Insights | Instagram Insights
23 | Brand | Fairness Report Monthly Views | 500 | 3,000 | 7,000 | Website page views + LinkedIn impressions | Google Analytics
24 | Brand | Corporate Accounts Signed | 0 | 5 | 15 | Active Wasel Business contracts (JD 25/mo) | CRM / QuickBooks