## Cover
WASEL
Year 1 Gantt · Execution Plan + Acquisition Strategy
Month 1 through Month 12 — Year-Long Roadmap
"To move Jordan forward — fairly."
CONFIDENTIAL – For Internal & Investor Use Only
Sheets in this workbook:
| TABLE 1 — Gantt Dataset | 111 tasks · relative dates · phase, workstream, owner, budget, milestone
| TABLE 2 — Gantt Visual | 52-week Gantt grid · colour-coded by phase · Month labels on columns
| Budget | Phased cost model by category · P&L summary
| KPI Dashboard | 25 KPIs across 5 categories · phase targets · data sources

## TABLE 1 — Gantt Dataset
ID | Phase | Start Wk | End Wk | Month | Workstream | Task / Deliverable | Owner | Budget (JD) | Milestone? | Duration (Wks)
1 | P0 | 1 | 1 | M1 | Legal | Incorporate company; appoint counsel; open bank account | Founder/Legal | JD 500 |  | 1
2 | P0 | 1 | 1 | M1 | Finance | Draft fundraising materials; update investor deck | Founder/CFO | — |  | 1
3 | P0 | 1 | 1 | M1 | Acquisition | Identify 5 founding driver ambassadors; build WhatsApp nucleus group | Founder | — |  | 1
4 | P0 | 2 | 2 | M1 | Legal | File LTRC operator licence application; JD 25K bank guarantee | Legal | JD 2,500 | ★ YES | 1
5 | P0 | 2 | 3 | M1–M1 | Finance | Launch seed round roadshow; investor meetings | Founder | — |  | 2
6 | P0 | 2 | 2 | M1 | Acquisition | Visit 10 taxi office managers in person; earnings comparison sheets | Founder/Ops | JD 100 |  | 1
7 | P0 | 3 | 3 | M1 | Legal | PDPL registration; draft driver and rider T&Cs | Legal | JD 300 |  | 1
8 | P0 | 3 | 3 | M1 | Ops | Define Amman pilot zone boundaries | COO | — |  | 1
9 | P0 | 3 | 3 | M1 | Acquisition | Launch driver waitlist landing page (WhatsApp-optimised) | CTO/Marketing | JD 400 | ★ YES | 1
10 | P0 | 4 | 4 | M1 | Tech | Issue RFPs for app development; select vendor | CTO | — |  | 1
11 | P0 | 4 | 4 | M1 | Acquisition | Field ambassador sessions at 3 fuel stations | Driver Rel | JD 100 |  | 1
12 | P0 | 5 | 5 | M1 | Finance | Close seed round; set up financial reporting | CFO/Founder | — | ★ YES | 1
13 | P0 | 5 | 5 | M1 | Tech | Sign dev contract; kick off sprint planning | CTO | JD 1,200 |  | 1
14 | P0 | 5 | 5 | M1 | Acquisition | Founding Driver Badge (Mu'assis) programme activated | Marketing | JD 200 | ★ YES | 1
15 | P0 | 6 | 6 | M1 | Legal | LTRC follow-up; register vehicles list | Legal | JD 500 |  | 1
16 | P0 | 6 | 6 | M1 | People | Hire Ops Manager, CX Lead, Marketing Lead (3 FTE) | Founder | JD 3,600 |  | 1
17 | P0 | 6 | 6 | M1 | Acquisition | Driver referral ladder activated; WhatsApp group seeding | Ops/Driver Rel | JD 300 |  | 1
18 | P1 | 7 | 7 | M2 | Tech | Sprint 1: Architecture, auth, user registration, map SDK | CTO/Dev | JD 4,000 |  | 1
19 | P1 | 7 | 7 | M2 | Brand | Finalise visual identity: logo, Arabic/EN typography | Marketing | JD 1,500 |  | 1
20 | P1 | 7 | 7 | M2 | Acquisition | Rider waitlist page live; Facebook organic content begins | Marketing | — |  | 1
21 | P1 | 8 | 8 | M2 | Tech | Sprint 2: Driver app core flow; subscription billing | Dev Team | JD 4,000 |  | 1
22 | P1 | 8 | 8 | M2 | Acquisition | Fuel station ambassador programme at 5 stations; target 50+ driver sign-ups | Driver Rel | JD 200 |  | 1
23 | P1 | 9 | 9 | M2 | Tech | Sprint 3: Rider app, real-time tracking, payments (CliQ/Visa) | Dev Team | JD 4,000 |  | 1
24 | P1 | 9 | 9 | M2 | Ops | Map Amman zones; define service hours; draft driver SOPs | COO | JD 400 |  | 1
25 | P1 | 9 | 9 | M2 | Acquisition | University campus ambassador programme — 3 campuses | Marketing | JD 270 |  | 1
26 | P1 | 10 | 10 | M2 | Tech | Sprint 4: Admin dashboard; KYC, analytics, notifications | Dev Team | JD 4,000 |  | 1
27 | P1 | 10 | 10 | M2 | Acquisition | TikTok content production — 2 driver testimonials filmed | Marketing | JD 400 |  | 1
28 | P1 | 11 | 11 | M3 | Tech | Sprint 5: Ratings, in-app chat, SOS, accessibility | Dev Team | JD 4,000 |  | 1
29 | P1 | 11 | 11 | M3 | Finance | Set up accounting; payroll; reporting template | CFO | JD 400 |  | 1
30 | P1 | 12 | 12 | M3 | Tech | Sprint 6: Surge cap logic; Wasel Pass/Go perk engine | Dev Team | JD 4,000 |  | 1
31 | P1 | 12 | 12 | M3 | Legal | Receive LTRC licence (expected); sign insurance policy | Legal | JD 2,200 | ★ YES | 1
32 | P1 | 13 | 13 | M3 | Tech | Sprint 7: Full integration and load testing (500 concurrent) | Dev/QA | JD 4,000 |  | 1
33 | P1 | 13 | 13 | M3 | Ops | Driver vehicle inspection protocol; partner 2 garages | COO | JD 800 |  | 1
34 | P1 | 13 | 13 | M3 | Acquisition | Target 200 driver sign-ups; paid Facebook ads if organic below pace | Marketing | JD 800 |  | 1
35 | P1 | 14 | 14 | M3 | Tech | Sprint 8: iOS App Store and Google Play submissions | CTO | JD 4,000 | ★ YES | 1
36 | P1 | 14 | 14 | M3 | Marketing | Branded merch design; order print run | Marketing | JD 2,400 |  | 1
37 | P1 | 15 | 15 | M3 | Tech | Sprint 9: App Store review cycle; v1.0 release candidate | Dev/CTO | JD 4,000 |  | 1
38 | P1 | 15 | 15 | M3 | Ops | Define driver support SLA; set up WhatsApp Business helpline | Ops Mgr | JD 300 |  | 1
39 | P1 | 15 | 15 | M3 | Acquisition | Rider referral mechanic live; campus ambassador rewards active | Marketing | JD 500 |  | 1
40 | P1 | 16 | 16 | M4 | Tech | Sprint 10: Final UAT; fix P0/P1 bugs; tag v1.0.0 | QA/Dev | JD 4,000 |  | 1
41 | P1 | 16 | 16 | M4 | Finance | Board update; investor report; cash flow vs budget | CFO | — |  | 1
42 | P1 | 17 | 17 | M4 | People | Hire CTO, 2 Driver Rel Officers, 1 Data Analyst | Founder/HR | JD 2,400 |  | 1
43 | P1 | 17 | 17 | M4 | Acquisition | Pre-launch driver recruitment campaign; mechanic shop materials placed | Marketing | JD 1,500 |  | 1
44 | P1 | 18 | 18 | M4 | Tech | Apps approved and live on stores (invite-only); prod infra scaled | CTO | JD 1,500 | ★ YES | 1
45 | P1 | 18 | 18 | M4 | Ops | STAGE GATE 1: Tech OK, LTRC confirmed, 50+ waitlist, team 8 FTE | Founder | — | ★ YES | 1
46 | P2 | 19 | 19 | M4 | Driver | M0 cohort: 30 drivers, free trial, KYC, inspection, training | Driver Rel | JD 1,200 |  | 1
47 | P2 | 19 | 19 | M4 | Acquisition | Boycott tailwind content campaign; Fairness Report #1 drafted | Marketing | JD 1,500 |  | 1
48 | P2 | 20 | 20 | M5 | Driver | Driver onboarding sessions (3 group sessions); branded kits | Driver Rel | JD 600 |  | 1
49 | P2 | 20 | 20 | M5 | Acquisition | Press outreach — local media "Fair Ride" story pitch | Marketing | JD 800 |  | 1
50 | P2 | 21 | 21 | M5 | Driver | Week 3 M0 feedback loop; survey all drivers; app hotfixes | CTO/Driver Rel | JD 2,000 |  | 1
51 | P2 | 21 | 21 | M5 | Ops | Internal ride testing: 20 employee testers; measure dispatch | COO | — |  | 1
52 | P2 | 22 | 22 | M5 | Driver | Open driver waitlist to public; target 100 total applications | Marketing/Ops | JD 1,800 |  | 1
53 | P2 | 22 | 22 | M5 | Finance | Month 6 financials; confirm burn rate; update runway | CFO | — |  | 1
54 | P2 | 23 | 23 | M5 | Driver | M0→M1 conversion: 20 drivers to JD 10/mo ramp tier | Driver Rel | JD 200 |  | 1
55 | P2 | 23 | 23 | M5 | Acquisition | "Save Your Seat" rider pre-registration viral campaign; 500 target | Marketing | JD 2,500 |  | 1
56 | P2 | 24 | 24 | M6 | Driver | M1 onboarding: 30 new drivers; target 50+ active M0/M1 | Driver Rel | JD 600 |  | 1
57 | P2 | 24 | 24 | M6 | Ops | Activate Wasel Go priority dispatch perk — tested in parallel | CTO/COO | JD 300 |  | 1
58 | P2 | 25 | 25 | M6 | Driver | Safety audit: re-inspect top 20 M0 drivers; certify pass/fail | Ops Mgr | JD 400 |  | 1
59 | P2 | 25 | 25 | M6 | Acquisition | Monthly Fairness Report #1 published | Marketing/Data | JD 600 | ★ YES | 1
60 | P2 | 26 | 26 | M6 | Ops | STAGE GATE 2: 80+ drivers, stable app, media coverage, 500+ pre-signups | Founder | — | ★ YES | 1
61 | P2 | 26 | 26 | M6 | Finance | Q2 management accounts; board update; Series A timeline | CFO | — |  | 1
62 | P3 | 27 | 27 | M6 | Launch | SOFT LAUNCH: 500 invite codes; PR push; TV interview | Founder/Marketing | JD 5,000 | ★ YES | 1
63 | P3 | 27 | 27 | M6 | Ops | War room: 3 ops staff; 1h SLA; daily standup | COO | — |  | 1
64 | P3 | 28 | 28 | M6 | Tech | Monitor crash rates, latency, dispatch; patches within 24h | CTO | JD 1,500 |  | 1
65 | P3 | 28 | 28 | M6 | Acquisition | Referral programme: Invite a Friend, Both Get 1 Month Wasel Go Free | Marketing | JD 3,000 | ★ YES | 1
66 | P3 | 29 | 29 | M7 | Driver | M1→M2 conversion: drivers earning >JD 50/wk offered Standard tier | Driver Rel | JD 400 |  | 1
67 | P3 | 29 | 29 | M7 | Ops | Dispatch algorithm review; adjust radius; target 85% success | CTO/COO | JD 800 |  | 1
68 | P3 | 30 | 30 | M7 | Rider | Wasel Pass open (JD 10/mo); "First Month Free" promotion | Marketing | JD 2,000 | ★ YES | 1
69 | P3 | 30 | 30 | M7 | Finance | Month 8 close: first real revenue; actuals vs model | CFO | — |  | 1
70 | P3 | 31 | 31 | M7 | Marketing | 3 micro-influencer partnerships (80K–200K followers) | Marketing | JD 2,500 |  | 1
71 | P3 | 31 | 31 | M7 | Tech | v1.1 release: ETA accuracy, dark mode, Arabic RTL, A/B onboarding | Dev Team | JD 4,000 | ★ YES | 1
72 | P3 | 32 | 32 | M7 | Driver | Driver Milestone Event: celebrate 100 active drivers | Ops/Marketing | JD 1,200 | ★ YES | 1
73 | P3 | 32 | 32 | M7 | Ops | Expand pilot zone: add Jabal Amman, Ras Al Ain, Wadi Seer | COO | JD 300 |  | 1
74 | P3 | 33 | 33 | M8 | Marketing | Fairness Report #2; "1K rides" milestone; Instagram AMA | Marketing | JD 600 |  | 1
75 | P3 | 33 | 33 | M8 | Finance | Investor update: KPIs vs projections; identify bridge needs | Founder/CFO | — |  | 1
76 | P3 | 34 | 34 | M8 | Tech | v1.2 release: scheduled rides, multi-stop, receipt export | Dev Team | JD 4,000 | ★ YES | 1
77 | P3 | 34 | 34 | M8 | Ops | SLA audit; analyse driver churn; adjust onboarding script | Ops Mgr | — |  | 1
78 | P3 | 35 | 35 | M8 | Driver | M2→M3 upgrade campaign: Plus and Pro tiers offered | Driver Rel | JD 300 |  | 1
79 | P3 | 35 | 35 | M8 | Acquisition | Corporate accounts outreach: 10 SMEs targeted; first B2B proposals | Founder/Marketing | JD 1,500 |  | 1
80 | P3 | 36 | 36 | M8 | Ops | STAGE GATE 3: 200+ drivers, 1000+ riders, revenue ✓, NPS >50 | Founder | — | ★ YES | 1
81 | P4 | 37 | 37 | M9 | Launch | FULL AMMAN LAUNCH: invite gates removed; paid media live | Marketing/CTO | JD 8,000 | ★ YES | 1
82 | P4 | 37 | 37 | M9 | Driver | Aggressive recruitment: target 500 drivers; JD 50 sign-on incentive | Driver Rel | JD 5,000 |  | 1
83 | P4 | 38 | 38 | M9 | Tech | Scale infra: AWS auto-scaling; CDN; circuit breakers | CTO | JD 3,000 |  | 1
84 | P4 | 38 | 38 | M9 | Marketing | OOH: 10 Amman billboards; bus shelter ads | Marketing | JD 6,000 |  | 1
85 | P4 | 39 | 39 | M9 | Rider | Wasel Business tier launch (JD 25/mo, 50 rides, no surge) | Founder/Ops | JD 1,000 | ★ YES | 1
86 | P4 | 39 | 39 | M9 | Finance | Month 9 close: target JD 30K+ revenue | CFO | — |  | 1
87 | P4 | 40 | 40 | M9 | Ops | Airport corridor activation; partner terminal management | COO | JD 2,000 | ★ YES | 1
88 | P4 | 40 | 40 | M9 | Marketing | Fairness Report #3; "10K rides" milestone campaign | Marketing | JD 1,500 |  | 1
89 | P4 | 41 | 41 | M9 | Tech | v1.3 release: Wasel Business portal, scheduled corporate pickups | Dev Team | JD 4,000 | ★ YES | 1
90 | P4 | 41 | 41 | M9 | Driver | Driver welfare: bank loan product partnership; wellness check-ins | Ops Mgr | JD 800 |  | 1
91 | P4 | 42 | 42 | M10 | Legal | LTRC licence renewal due diligence; annual report submission | Legal | JD 1,000 |  | 1
92 | P4 | 42 | 42 | M10 | Finance | Series A prep: financial advisor appointed; data room built | CFO/Founder | JD 2,000 | ★ YES | 1
93 | P4 | 43 | 43 | M10 | Marketing | Holiday season campaign planning; high-demand promotions | Marketing | JD 2,000 |  | 1
94 | P4 | 43 | 43 | M10 | Ops | Second-city expansion scoping: market assessment and LTRC mapping | COO | JD 1,200 |  | 1
95 | P4 | 44 | 44 | M10 | People | Year-end review; salary benchmarking; hire Year 2 roles | Founder/HR | JD 3,600 |  | 1
96 | P4 | 44 | 44 | M10 | Finance | STAGE GATE 4: 400+ drivers, 5000+ riders, JD 35K/mo, NPS >60 | Founder | — | ★ YES | 1
97 | P5 | 45 | 52 | M10–M12 | Finance | Series A roadshow: 15 VC/FO meetings; target close Year 2 Q2 | Founder/CFO | — | ★ YES | 8
98 | P5 | 46 | 46 | M11 | Tech | v2.0 planning: Pool, Ladies, AI dispatch optimisation | CTO | JD 2,000 |  | 1
99 | P5 | 46 | 48 | M11–M11 | Ops | Second-city soft launch preparation: 20 drivers waitlisted | COO | JD 1,500 |  | 3
100 | P5 | 47 | 47 | M11 | Marketing | Fairness Report #4; "50K rides" milestone; documentary short film | Marketing | JD 3,000 | ★ YES | 1
101 | P5 | 47 | 47 | M11 | Finance | Year-end audit; statutory filing; board approval | CFO/Auditor | JD 3,500 |  | 1
102 | P5 | 48 | 48 | M11 | Tech | Data platform: Metabase, event tracking, LTV dashboards | Data/CTO | JD 2,500 |  | 1
103 | P5 | 48 | 48 | M11 | Ops | Second-city launch: 20 drivers, invite-only, replicate playbook | COO | JD 3,000 | ★ YES | 1
104 | P5 | 49 | 49 | M11 | Marketing | Peak season campaign prep; charity partnership tie-in | Marketing | JD 1,500 |  | 1
105 | P5 | 49 | 49 | M11 | Finance | Series A due diligence: data room access to 3 lead investors | CFO | — |  | 1
106 | P5 | 50 | 51 | M12–M12 | Tech | v2.0 Sprint 1: Pool architecture; ride-matching algorithm design | CTO/Dev | JD 4,000 |  | 2
107 | P5 | 50 | 50 | M12 | Ops | Annual operational review: driver survey, NPS bench, CAC analysis | COO | — |  | 1
108 | P5 | 51 | 51 | M12 | Finance | Year 2 Q1 budget; LTRC renewal payment (JD 100K); update 3-yr model | CFO | JD 100,000 | ★ YES | 1
109 | P5 | 51 | 51 | M12 | Marketing | Brand refresh assessment; update Year 2 messaging | Marketing | JD 1,000 |  | 1
110 | P5 | 52 | 52 | M12 | Ops | STAGE GATE 5 / YEAR-END: KPIs, Series A, 2nd city, 600+ drivers | Founder | — | ★ YES | 1
111 | P5 | 52 | 52 | M12 | Finance | Shareholder annual meeting; Year 1 financials; Year 2 strategy | Founder/CFO | — | ★ YES | 1
[5 empty] | TOTAL YEAR 1 BUDGET |  |  | JD 267,970

## TABLE 2 — Gantt Visual
ID | Phase | Workstream | Task / Deliverable | Owner | W1 M1 | W2 M1 | W3 M1 | W4 M1 | W5 M1 | W6 M1 | W7 M2 | W8 M2 | W9 M2 | W10 M2 | W11 M3 | W12 M3 | W13 M3 | W14 M3 | W15 M3 | W16 M4 | W17 M4 | W18 M4 | W19 M4 | W20 M5 | W21 M5 | W22 M5 | W23 M5 | W24 M6 | W25 M6 | W26 M6 | W27 M6 | W28 M6 | W29 M7 | W30 M7 | W31 M7 | W32 M7 | W33 M8 | W34 M8 | W35 M8 | W36 M8 | W37 M9 | W38 M9 | W39 M9 | W40 M9 | W41 M9 | W42 M10 | W43 M10 | W44 M10 | W45 M10 | W46 M11 | W47 M11 | W48 M11 | W49 M11 | W50 M12 | W51 M12 | W52 M12
1 | P0 | Legal | Incorporate company; appoint counsel; open bank account | Founder/Legal
2 | P0 | Finance | Draft fundraising materials; update investor deck | Founder/CFO
3 | P0 | Acquisition | Identify 5 founding driver ambassadors; build WhatsApp ... | Founder
4 | P0 | Legal | File LTRC operator licence application; JD 25K bank gua... ★ | Legal
5 | P0 | Finance | Launch seed round roadshow; investor meetings | Founder
6 | P0 | Acquisition | Visit 10 taxi office managers in person; earnings compa... | Founder/Ops
7 | P0 | Legal | PDPL registration; draft driver and rider T&Cs | Legal
8 | P0 | Ops | Define Amman pilot zone boundaries | COO
9 | P0 | Acquisition | Launch driver waitlist landing page (WhatsApp-optimised... ★ | CTO/Marketing
10 | P0 | Tech | Issue RFPs for app development; select vendor | CTO
11 | P0 | Acquisition | Field ambassador sessions at 3 fuel stations | Driver Rel
12 | P0 | Finance | Close seed round; set up financial reporting ★ | CFO/Founder
13 | P0 | Tech | Sign dev contract; kick off sprint planning | CTO
14 | P0 | Acquisition | Founding Driver Badge (Mu'assis) programme activated ★ | Marketing
15 | P0 | Legal | LTRC follow-up; register vehicles list | Legal
16 | P0 | People | Hire Ops Manager, CX Lead, Marketing Lead (3 FTE) | Founder
17 | P0 | Acquisition | Driver referral ladder activated; WhatsApp group seedin... | Ops/Driver Rel
18 | P1 | Tech | Sprint 1: Architecture, auth, user registration, map SD... | CTO/Dev
19 | P1 | Brand | Finalise visual identity: logo, Arabic/EN typography | Marketing
20 | P1 | Acquisition | Rider waitlist page live; Facebook organic content begi... | Marketing
21 | P1 | Tech | Sprint 2: Driver app core flow; subscription billing | Dev Team
22 | P1 | Acquisition | Fuel station ambassador programme at 5 stations; target... | Driver Rel
23 | P1 | Tech | Sprint 3: Rider app, real-time tracking, payments (CliQ... | Dev Team
24 | P1 | Ops | Map Amman zones; define service hours; draft driver SOP... | COO
25 | P1 | Acquisition | University campus ambassador programme — 3 campuses | Marketing
26 | P1 | Tech | Sprint 4: Admin dashboard; KYC, analytics, notification... | Dev Team
27 | P1 | Acquisition | TikTok content production — 2 driver testimonials filme... | Marketing
28 | P1 | Tech | Sprint 5: Ratings, in-app chat, SOS, accessibility | Dev Team
29 | P1 | Finance | Set up accounting; payroll; reporting template | CFO
30 | P1 | Tech | Sprint 6: Surge cap logic; Wasel Pass/Go perk engine | Dev Team
31 | P1 | Legal | Receive LTRC licence (expected); sign insurance policy ★ | Legal
32 | P1 | Tech | Sprint 7: Full integration and load testing (500 concur... | Dev/QA
33 | P1 | Ops | Driver vehicle inspection protocol; partner 2 garages | COO
34 | P1 | Acquisition | Target 200 driver sign-ups; paid Facebook ads if organi... | Marketing
35 | P1 | Tech | Sprint 8: iOS App Store and Google Play submissions ★ | CTO
36 | P1 | Marketing | Branded merch design; order print run | Marketing
37 | P1 | Tech | Sprint 9: App Store review cycle; v1.0 release candidat... | Dev/CTO
38 | P1 | Ops | Define driver support SLA; set up WhatsApp Business hel... | Ops Mgr
39 | P1 | Acquisition | Rider referral mechanic live; campus ambassador rewards... | Marketing
40 | P1 | Tech | Sprint 10: Final UAT; fix P0/P1 bugs; tag v1.0.0 | QA/Dev
41 | P1 | Finance | Board update; investor report; cash flow vs budget | CFO
42 | P1 | People | Hire CTO, 2 Driver Rel Officers, 1 Data Analyst | Founder/HR
43 | P1 | Acquisition | Pre-launch driver recruitment campaign; mechanic shop m... | Marketing
44 | P1 | Tech | Apps approved and live on stores (invite-only); prod in... ★ | CTO
45 | P1 | Ops | STAGE GATE 1: Tech OK, LTRC confirmed, 50+ waitlist, te... ★ | Founder
46 | P2 | Driver | M0 cohort: 30 drivers, free trial, KYC, inspection, tra... | Driver Rel
47 | P2 | Acquisition | Boycott tailwind content campaign; Fairness Report #1 d... | Marketing
48 | P2 | Driver | Driver onboarding sessions (3 group sessions); branded ... | Driver Rel
49 | P2 | Acquisition | Press outreach — local media "Fair Ride" story pitch | Marketing
50 | P2 | Driver | Week 3 M0 feedback loop; survey all drivers; app hotfix... | CTO/Driver Rel
51 | P2 | Ops | Internal ride testing: 20 employee testers; measure dis... | COO
52 | P2 | Driver | Open driver waitlist to public; target 100 total applic... | Marketing/Ops
53 | P2 | Finance | Month 6 financials; confirm burn rate; update runway | CFO
54 | P2 | Driver | M0→M1 conversion: 20 drivers to JD 10/mo ramp tier | Driver Rel
55 | P2 | Acquisition | "Save Your Seat" rider pre-registration viral campaign;... | Marketing
56 | P2 | Driver | M1 onboarding: 30 new drivers; target 50+ active M0/M1 | Driver Rel
57 | P2 | Ops | Activate Wasel Go priority dispatch perk — tested in pa... | CTO/COO
58 | P2 | Driver | Safety audit: re-inspect top 20 M0 drivers; certify pas... | Ops Mgr
59 | P2 | Acquisition | Monthly Fairness Report #1 published ★ | Marketing/Data
60 | P2 | Ops | STAGE GATE 2: 80+ drivers, stable app, media coverage, ... ★ | Founder
61 | P2 | Finance | Q2 management accounts; board update; Series A timeline | CFO
62 | P3 | Launch | SOFT LAUNCH: 500 invite codes; PR push; TV interview ★ | Founder/Marketing
63 | P3 | Ops | War room: 3 ops staff; 1h SLA; daily standup | COO
64 | P3 | Tech | Monitor crash rates, latency, dispatch; patches within ... | CTO
65 | P3 | Acquisition | Referral programme: Invite a Friend, Both Get 1 Month W... ★ | Marketing
66 | P3 | Driver | M1→M2 conversion: drivers earning >JD 50/wk offered Sta... | Driver Rel
67 | P3 | Ops | Dispatch algorithm review; adjust radius; target 85% su... | CTO/COO
68 | P3 | Rider | Wasel Pass open (JD 10/mo); "First Month Free" promotio... ★ | Marketing
69 | P3 | Finance | Month 8 close: first real revenue; actuals vs model | CFO
70 | P3 | Marketing | 3 micro-influencer partnerships (80K–200K followers) | Marketing
71 | P3 | Tech | v1.1 release: ETA accuracy, dark mode, Arabic RTL, A/B ... ★ | Dev Team
72 | P3 | Driver | Driver Milestone Event: celebrate 100 active drivers ★ | Ops/Marketing
73 | P3 | Ops | Expand pilot zone: add Jabal Amman, Ras Al Ain, Wadi Se... | COO
74 | P3 | Marketing | Fairness Report #2; "1K rides" milestone; Instagram AMA | Marketing
75 | P3 | Finance | Investor update: KPIs vs projections; identify bridge n... | Founder/CFO
76 | P3 | Tech | v1.2 release: scheduled rides, multi-stop, receipt expo... ★ | Dev Team
77 | P3 | Ops | SLA audit; analyse driver churn; adjust onboarding scri... | Ops Mgr
78 | P3 | Driver | M2→M3 upgrade campaign: Plus and Pro tiers offered | Driver Rel
79 | P3 | Acquisition | Corporate accounts outreach: 10 SMEs targeted; first B2... | Founder/Marketing
80 | P3 | Ops | STAGE GATE 3: 200+ drivers, 1000+ riders, revenue ✓, NP... ★ | Founder
81 | P4 | Launch | FULL AMMAN LAUNCH: invite gates removed; paid media liv... ★ | Marketing/CTO
82 | P4 | Driver | Aggressive recruitment: target 500 drivers; JD 50 sign-... | Driver Rel
83 | P4 | Tech | Scale infra: AWS auto-scaling; CDN; circuit breakers | CTO
84 | P4 | Marketing | OOH: 10 Amman billboards; bus shelter ads | Marketing
85 | P4 | Rider | Wasel Business tier launch (JD 25/mo, 50 rides, no surg... ★ | Founder/Ops
86 | P4 | Finance | Month 9 close: target JD 30K+ revenue | CFO
87 | P4 | Ops | Airport corridor activation; partner terminal managemen... ★ | COO
88 | P4 | Marketing | Fairness Report #3; "10K rides" milestone campaign | Marketing
89 | P4 | Tech | v1.3 release: Wasel Business portal, scheduled corporat... ★ | Dev Team
90 | P4 | Driver | Driver welfare: bank loan product partnership; wellness... | Ops Mgr
91 | P4 | Legal | LTRC licence renewal due diligence; annual report submi... | Legal
92 | P4 | Finance | Series A prep: financial advisor appointed; data room b... ★ | CFO/Founder
93 | P4 | Marketing | Holiday season campaign planning; high-demand promotion... | Marketing
94 | P4 | Ops | Second-city expansion scoping: market assessment and LT... | COO
95 | P4 | People | Year-end review; salary benchmarking; hire Year 2 roles | Founder/HR
96 | P4 | Finance | STAGE GATE 4: 400+ drivers, 5000+ riders, JD 35K/mo, NP... ★ | Founder
97 | P5 | Finance | Series A roadshow: 15 VC/FO meetings; target close Year... ★ | Founder/CFO
98 | P5 | Tech | v2.0 planning: Pool, Ladies, AI dispatch optimisation | CTO
99 | P5 | Ops | Second-city soft launch preparation: 20 drivers waitlis... | COO
100 | P5 | Marketing | Fairness Report #4; "50K rides" milestone; documentary ... ★ | Marketing
101 | P5 | Finance | Year-end audit; statutory filing; board approval | CFO/Auditor
102 | P5 | Tech | Data platform: Metabase, event tracking, LTV dashboards | Data/CTO
103 | P5 | Ops | Second-city launch: 20 drivers, invite-only, replicate ... ★ | COO
104 | P5 | Marketing | Peak season campaign prep; charity partnership tie-in | Marketing
105 | P5 | Finance | Series A due diligence: data room access to 3 lead inve... | CFO
106 | P5 | Tech | v2.0 Sprint 1: Pool architecture; ride-matching algorit... | CTO/Dev
107 | P5 | Ops | Annual operational review: driver survey, NPS bench, CA... | COO
108 | P5 | Finance | Year 2 Q1 budget; LTRC renewal payment (JD 100K); updat... ★ | CFO
109 | P5 | Marketing | Brand refresh assessment; update Year 2 messaging | Marketing
110 | P5 | Ops | STAGE GATE 5 / YEAR-END: KPIs, Series A, 2nd city, 600+... ★ | Founder
111 | P5 | Finance | Shareholder annual meeting; Year 1 financials; Year 2 s... ★ | Founder/CFO

## Budget
WASEL — Year 1 Budget Breakdown (JD) · Phases & Categories
Cost Category | P0 (M1–M2) | P1 (M2–M5) | P2 (M5–M7) | P3 (M7–M10) | P4 (M10–M12) | P5 (M12) | TOTAL (JD) | % of Total
Personnel (salaries + NSSF 21.75%) | JD 8,700 | JD 28,000 | JD 19,200 | JD 26,400 | JD 36,000 | JD 24,000 | JD 142,300 | 31.53%
Technology (development + infrastructure) | JD 1,200 | JD 42,500 | JD 2,300 | JD 12,000 | JD 8,000 | JD 8,500 | JD 74,500 | 16.51%
Acquisition (pre-launch driver & rider) | JD 2,000 | JD 5,000 | JD 7,000 | JD 8,000 | JD 3,000 | — | JD 25,000 | 5.54%
Marketing & Brand (post-launch) | JD 600 | JD 2,800 | — | JD 6,600 | JD 16,000 | JD 5,500 | JD 31,500 | 6.98%
Legal & Regulatory | JD 3,800 | JD 2,700 | — | — | JD 1,500 | — | JD 8,000 | 1.773%
Operations & Driver Relations | — | JD 1,100 | JD 2,600 | JD 3,200 | JD 10,000 | JD 4,500 | JD 21,400 | 4.742%
Finance & Professional Services | JD 400 | JD 800 | — | — | JD 2,000 | JD 3,500 | JD 6,700 | 1.485%
LTRC Annual Licence Fee | — | — | — | — | — | JD 100,000 | JD 100,000 | 22.16%
Bank Guarantee (one-time deposit) | JD 25,000 | — | — | — | — | — | JD 25,000 | 5.54%
Contingency (5%) | JD 2,100 | JD 4,200 | JD 1,500 | JD 2,800 | JD 3,800 | JD 2,500 | JD 16,900 | 3.745%
GRAND TOTAL | JD 43,800 | JD 87,100 | JD 32,600 | JD 59,000 | JD 80,300 | JD 148,500 | JD 451,300 | 100%
Year 1 Revenue & P&L Summary
Driver Subscription Revenue | JD 154,000 |  | Monthly fee × active drivers (blended tier mix)
Rider Subscription Revenue | JD 130,000 |  | Wasel Go + Wasel Pass + Business accounts
TOTAL REVENUE (Year 1) | JD 284,000 |  | No fare commission — Wasel takes zero from trips
Total Operating Cost | JD 451,300 |  | Per budget above
Net Operating Loss | JD (167,300) |  | Revenue minus total costs
Seed Raise Target | JD 472,000 |  | ~$665,000 USD at 1 JD = $1.41
Implied Runway | ~14 months |  | From seed close to Stage Gate 5 / Series A

## KPI Dashboard
WASEL — KPI Dashboard (25 Metrics · 5 Categories)
# | Category | Metric | P3 Target | P4 Target | P5 Target | Definition | Source / Tool
1 | Growth | Active Drivers (≥1 trip/week) | 200 | 400 | 600+ | Drivers completing ≥1 trip in 7-day window | Admin dashboard
2 | Growth | Registered Riders | 1,000 | 5,000 | 8,000 | Total user accounts created in rider app | App database
3 | Growth | Monthly Active Riders (MAR) | 600 | 3,000 | 5,000 | Riders completing ≥1 trip in calendar month | App database
4 | Growth | Driver MoM Growth Rate | 15% | 20% | 10% | (New drivers / Prior month drivers) − 1 | Admin dashboard
5 | Growth | Rider MoM Growth Rate | 25% | 28% | 15% | (New riders / Prior month riders) − 1 | App database
6 | Growth | Waitlist → Active Driver Conversion | ≥60% | ≥65% | ≥70% | Activated drivers / total waitlist sign-ups | CRM pipeline
7 | Revenue | Monthly Revenue (JD) | 12,000 | 35,000 | 48,000 | Driver + rider subscriptions + corporate | QuickBooks
8 | Revenue | Driver Sub Attach Rate | 60% | 70% | 75% | Paying active drivers / total active drivers | Admin dashboard
9 | Revenue | Rider Sub Attach Rate | 35% | 40% | 42% | Subscriber riders / MAR | App database
10 | Revenue | ARPU — Driver (monthly) | JD 18 | JD 24 | JD 28 | Driver sub revenue / active drivers | QuickBooks
11 | Revenue | ARPU — Rider (monthly) | JD 4.20 | JD 5.50 | JD 6.00 | Rider sub revenue / MAR | QuickBooks
12 | Revenue | Monthly Burn Rate | < JD 55K | < JD 70K | < JD 80K | Total operating expenses in month | QuickBooks
13 | Revenue | Cash Runway (months) | >8 | >6 | >4 | Cash balance / monthly burn rate | CFO dashboard
14 | Acquisition | Driver Waitlist Sign-ups | 200 | 350 | 500+ | Cumulative since programme launch | CRM
15 | Acquisition | Rider Pre-registrations | 400 | 800 | 2,000+ | Cumulative waitlist + pre-signups | CRM
16 | Acquisition | Taxi Office Partnerships | 5 | 12 | 20 | Active partnerships signed | Ops log
17 | Acquisition | Driver Referral Conversion | 40% | 50% | 55% | Referred drivers who activate | CRM
18 | Acquisition | Driver CAC (blended, JD) | < 15 | < 12 | < 10 | Total acq spend / new active drivers | Finance
19 | Ops | Dispatch Success Rate | 80% | 88% | 92% | Matched trips / total requests in zone | Backend analytics
20 | Ops | Average ETA (minutes) | < 8 | < 6 | < 5 | Booking confirmed → driver arrives | App telemetry
21 | Ops | Driver Average Rating | ≥ 4.5 | ≥ 4.6 | ≥ 4.7 | Post-trip rider rating, 5-point scale | App database
22 | Ops | Driver Monthly Churn | < 12% | < 9% | < 7% | Cancellations / active drivers at month start | Admin dashboard
23 | Ops | Rider Retention (M+1) | 40% | 50% | 60% | Riders who rode in month N and ride again N+1 | Metabase cohort
24 | Brand | Net Promoter Score (NPS) | >50 | >60 | >65 | Post-trip survey, quarterly sample ≥200 | In-app survey
25 | Brand | Monthly Fairness Report Views | 500 | 3,000 | 7,000 | Website analytics + LinkedIn reach | Google Analytics