WASEL

Year 1 Master Plan

Execution Timeline · Acquisition Strategy · Budget · KPIs

Month 1 through Month 12

"To move Jordan forward — fairly."

CONFIDENTIAL — For Internal & Investor Use Only

| Document Version | 1.1 — Combined Master Plan |
| --- | --- |
| Prepared by | Wasel Founding Team |
| Review Cycle | Monthly — updated after each Stage Gate |
| Total Planned Budget (Year 1) | JD 472,000 (~$665K) |
| Seed Round Target | JD 472,000 |
| Target Launch | End of Month 7 (Soft) · Month 10 (Full Amman) |
| Year-End Target — Drivers | 500+ active |
| Year-End Target — Riders | 8,000+ registered |
| Sections | 1 Executive Summary · 2 Assumptions · 3 Acquisition Strategy · 4 Workstreams · 5 Phases · 6 Weekly Plan · 7 Budget · 8 KPIs · 9 Risks · 10 Launch Playbook · 11 Checklist · 12 Appendix |

# Table of Contents

Table of Contents	2

1. Executive Summary	3

2. Key Assumptions	4

3. Pre-Launch Acquisition Strategy	5

Driver Archetypes	6

Offline Channels — The Engine Room	6

Online Channels — Amplification	7

Skepticism Handling	7

4. Workstreams & Owners	11

5. Phase Plan & Stage Gates	12

6. Week-by-Week Execution Plan	13

7. Cost Model & Budget Breakdown	18

8. KPI Dashboard Specification	19

9. Risk Register	21

10. Launch Playbook — Day −14 to Day +14	22

11. Final Deliverables Checklist	24

12. Appendix: Definitions and Glossary	26

# 1. Executive Summary

Wasel is Jordan's first subscription-based ride-hailing platform. Drivers pay a flat monthly fee (JD 20–55 depending on tier) and keep 100% of every fare — replacing the 30% commission extracted by incumbent platforms. This document is the complete Year 1 operating guide: what to build, who does it, when, at what cost, and how to acquire the drivers and riders the platform needs to succeed.

WHY WASEL, WHY NOW

Three structural conditions make this the right moment to launch. First, a major incumbent platform made a highly publicised investment in an Israeli defence-technology company, triggering a strong boycott movement among Jordanian drivers and riders. This creates a 1.25× acquisition efficiency multiplier that must be captured within the launch window. Second, no existing Jordanian platform uses a subscription model — every competitor takes commission, which means every driver is financially worse off every single month. Third, Jordan's ride-hailing market has no dominant local brand. The category is owned by multinationals. Wasel can own the "Jordanian" identity permanently if it moves fast and executes well.

FINANCIAL HEADLINES

| Seed Raise Target | JD 472,000 (~$665,000 USD) |
| --- | --- |
| Year 1 Revenue (projected) | JD 284,000 |
| — Driver Subscriptions | JD 154,000 |
| — Rider Subscriptions | JD 130,000 |
| Year 1 Net Operating Loss | JD 726,000 |
| Runway at Seed Close | ~14 months to Stage Gate 5 / Series A |
| Fare vs Incumbent | JD 2.37/trip — 5% below Uber/Careem |
| Driver Tiers | Standard JD 20/mo · Plus JD 35/mo · Pro JD 55/mo |
| Rider Tiers | Wasel Go JD 5/mo (perks) · Wasel Pass JD 10/mo · Business JD 25/mo |

YEAR 1 IN SIX PHASES

| Phase 0 · Foundation (M1–M2) | Legal incorporation, LTRC licence, seed close, vendor selection, founding driver ambassador recruitment |
| --- | --- |
| Phase 1 · Build (M2–M5) | 10 development sprints, app store launch, team hiring, brand, driver waitlist to 200+ |
| Phase 2 · Driver Onboarding (M5–M7) | 80+ drivers activated through M0/M1 cohort ramp; rider pre-registration campaign |
| Phase 3 · Soft Launch (M7–M10) | 500 invite codes; referral programme; subscriptions open; 200+ drivers; 1,000+ riders |
| Phase 4 · Full Launch (M10–M12) | Remove gates; paid media; OOH; airport corridor; corporate accounts; 400+ drivers |
| Phase 5 · Scale & Series A (M12) | Second-city expansion; v2.0 planning; Series A roadshow; annual review |

# 2. Key Assumptions

All budget lines, headcount plans, and KPI targets in this document depend on the following assumptions. They should be reviewed at every Stage Gate and updated with actual data.

MARKET AND REGULATORY

| Assumption | Base Case | Stress Case |
| --- | --- | --- |
| LTRC licence granted | Month 3 | Month 4–5 |
| LTRC annual fee | JD 100,000/year | JD 120,000/year |
| Bank guarantee required | JD 25,000 | JD 25,000 |
| Seed round close | Month 2 | Month 3 |
| App development cost | JD 40,000 (10 sprints) | JD 50,000 |
| Boycott tailwind multiplier | 1.25× acquisition efficiency | 1.0× (fades by Month 8) |
| JD/USD exchange rate | 1 JD = $1.41 USD | 1 JD = $1.41 USD |

DRIVER ECONOMICS

| Average trips/day (Standard driver, capped) | 8 trips |
| --- | --- |
| Average fare per trip | JD 2.37 (5% below incumbent market rate) |
| Driver gross monthly revenue (Standard, 22 working days) | JD 417 |
| Subscription fee (Standard tier) | JD 20/month |
| Driver net monthly revenue (Standard) | JD 397 |
| Equivalent net monthly revenue on Uber/Careem (30% commission) | JD 306 |
| Wasel driver uplift vs incumbent | + JD 91/month (+30%) |
| M0 (trial) duration and cost to driver | 1 month, free |
| M1 (ramp) subscription fee | JD 10/month |
| M0 → M2 conversion rate (target) | 60% |
| Monthly driver churn (steady state) | 8% |

RIDER ECONOMICS

| Wasel Go monthly fee | JD 5/month — perks only, no fare discount |
| --- | --- |
| Wasel Pass monthly fee | JD 10/month — all Go perks plus 1 free ride/month |
| Wasel Business monthly fee | JD 25/month — 50 rides, no surge, central billing |
| Cost to Wasel per perk delivered | JD 0 (operational, not monetary) |
| Rider MoM growth rate (Months 7–10) | 25–30% |
| Year-end target riders | 8,000 registered / 4,000 active |
| Rider subscription attach rate (target) | 35% of active riders |

# 3. Pre-Launch Acquisition Strategy

This section is the acquisition playbook for Wasel's pre-launch period. It covers driver acquisition (the most critical task), rider acquisition, promotions and incentives, sign-up mechanics, and budget scenarios across three capital levels. Every recommendation is specific to the Jordanian market — not generic marketing advice.

3.0  FIVE TRUTHS ABOUT THE JORDANIAN MARKET

| TRUTH 1 — Cynicism is your biggest competitor | Most drivers have encountered failed ride-hailing platforms. Your biggest obstacle is not Uber — it is driver skepticism. Every tactic in this plan is designed to remove risk rather than pitch features. |
| --- | --- |

| TRUTH 2 — WhatsApp is the substrate | Jordan runs on WhatsApp. Every critical interaction — sign-up, onboarding, support, referral — must be completable via WhatsApp. If a driver must open an unfamiliar app to complete a step, you lose him at that step. |
| --- | --- |

| TRUTH 3 — Go to the nodes, not the individuals | Taxi office managers each control 15–40 drivers. One converted manager is worth 20 individual sign-ups. The drivers follow their manager's endorsement. Win the node; the network follows. |
| --- | --- |

| TRUTH 4 — The boycott gets them in; quality keeps them | The anti-incumbent sentiment is real but fragile. It is emotionally driven, not rationally locked in. A driver or rider who joins because of ethics will leave immediately if the product disappoints. Ethics opens the door; execution keeps it open. |
| --- | --- |

| TRUTH 5 — Dignity before price | A driver who earns JD 15 more per month with Wasel will stay if you treat him with respect. He will leave if a competitor pays JD 5 more but makes him feel like a gig worker. Design every interaction around dignity, not just earnings. |
| --- | --- |

3.1  WAITLIST STRATEGY ARCHITECTURE

The waitlist is not a holding room — it is the first product experience. How it is framed determines whether it creates commitment or indifference.

| Frame | Language |
| --- | --- |
| WRONG — Queuing frame | CORRECT — Ownership frame |
| "Sign up to be notified at launch" | "Claim your Founding Member position — only 500 available" |
| "We'll let you know when we're ready" | "Your position in Wasel history is reserved. You are #247." |
| "Join our waitlist" | "Become a Wasel Mu'assis (Founder)" |
| "Early access coming soon" | "Founding drivers shape the platform. Your first month is free." |
| "Thank you for your interest" | "You're in. Tell two drivers — they'll thank you later." |

Waitlist position also determines subscription discounts, creating an organic urgency engine:

| Position | Driver Discount | Rider Discount | Why It Works |
| --- | --- | --- | --- |
| #1–100 | 50% off for 6 months | 3 months Wasel Go free | First movers get the best deal — urgency to sign up early and refer fast |
| #101–300 | 30% off for 4 months | 2 months Wasel Go free | Compelling offer; referrers have reason to push friends before position 300 |
| #301–600 | 20% off for 2 months | 1 month Wasel Go free | Solid baseline — still better than zero |
| #601+ | Standard rates | 1 free ride at launch | Converts passives; no special status |

3.2  DRIVER ACQUISITION PLAN

## Driver Archetypes

| Archetype | Profile | Core Fear | What Unlocks Him |
| --- | --- | --- | --- |
| The Freelancer (60%) | Age 20–35, owns car, full-time TNC driver, family obligations | Income volatility — losing Uber's demand network | Show the monthly earnings calculator with real JD numbers, not percentages |
| The Supplemental (25%) | Government worker or semi-retired, drives evenings/weekends, car owned outright | Wasted effort — doesn't want to manage two apps | Simple flat-fee pitch: "JD 20/month. Keep everything else." Three sentences. |
| The Taxi Office Driver (15%) | Drives under a taxi office arrangement, shared earnings with office manager | Losing existing arrangement — the office provides a safety net | Win the office manager first. Never pitch these drivers directly. |

## Offline Channels — The Engine Room

Offline channels drive driver acquisition. Online channels amplify it. Reverse this order and you waste money on low-trust impressions.

Fuel stations: Every working driver visits one at least once daily. A field ambassador (an already-onboarded Wasel driver, not a marketing employee) stations himself at the pump during peak hours. He starts with "Is Uber hard on you lately?" and lets the conversation flow. He shows his phone — his Mu'assis badge, his earnings screen. He does not pitch. He demonstrates. Target stations: high-TNC-traffic locations near the airport corridor, University Street, working-class residential zones, and the Zarqa road transition. Cost: JD 0 in cash — the ambassador wears a Wasel hoodie and a branded phone mount.

Taxi offices: One converted office manager yields 10–25 drivers. Visit in person, morning, never cold-message. Bring a printed earnings comparison sheet and buy tea. Open with: "How much does commission cost your drivers each month?" Let him calculate. Then show the sheet: "Driver doing 9 trips/day on Uber keeps JD 12.70 after commission. Same driver on Wasel keeps JD 21.33 minus JD 20/month — net difference JD 248/month." Offer a partnership plaque for the office wall and a monthly earnings report for his drivers. Give him 10 printed QR cards with his name as referrer. He earns social capital with every driver who joins. Target first: high-density offices in Ras Al Ain, Hai Nazzal, Tabarbour, Al-Hashimi Al-Shamali.

Mechanic shops: Drivers wait 45 minutes to 3 hours for service. Wasel materials in waiting areas create repeated passive impressions. Partner with the top 20 driver-frequented mechanics: Wasel materials displayed in exchange for a small discount coupon to any driver who shows confirmed Wasel registration. Cost: JD 50 in print materials.

WhatsApp groups: Jordan's driver community organises in large WhatsApp groups (Uber drivers, Careem drivers, taxi associations, neighbourhood networks). These groups are moderated and respected — blasting them gets you banned. Approach admins personally through existing drivers. Seed questions through trusted members, not brand posts. Create an invitation-only Wasel driver group called "Mu'assisun Wasel" — membership by driver referral only. The exclusivity is the point.

## Online Channels — Amplification

Facebook remains the primary social network for Jordanian drivers aged 28–55. Target large Jordanian TNC driver groups with genuine value content — earnings calculators, regulatory updates, maintenance advice — before any promotional posts. Run paid Facebook ads only to lookalike audiences built from your existing waitlist phone numbers. TikTok driver content (unscripted, dashboard-filmed earnings videos) has high organic reach potential among working-age men. One viral video can replace JD 5,000 of paid acquisition.

## Skepticism Handling

"This sounds too good to be true" is not an objection to overcome with more information — it is a request for risk removal. Respond to every skepticism trigger by eliminating risk, not adding features.

| Trigger | Risk-Removal Response |
| --- | --- |
| "This sounds like another platform that will fail." | Share the LTRC licence number, company registration, and physical Amman office address. "We are registered, regulated, and real. Come visit us." |
| "What if Wasel shuts down?" | "Your first month is free. If we shut down, you've lost nothing. You can return to Uber tomorrow. We are not asking you to burn your backup." |
| "I won't get enough rides without the Uber network." | "Your first month costs you nothing. Use both. See which pays better. We are not asking you to choose until you have evidence." |
| "My income will drop during the switch." | "We guarantee founding drivers a JD 350/month earnings floor for their first paid month. If we don't deliver, we refund the subscription fee." [First 50 drivers only — budget accordingly] |
| "I don't want to leave my taxi office." | "Many of our drivers keep their office relationships. Wasel adds rides on top — it does not require you to leave anything behind." |

3.3  RIDER ACQUISITION PLAN

Do not launch rider acquisition until 60+ active drivers are verified in the pilot zone. Premature demand with inadequate supply destroys early adopters — exactly the high-trust, word-of-mouth users you need most.

| Segment | Profile | Primary Motivation | Best Channel |
| --- | --- | --- | --- |
| University Students | Age 18–25, price-sensitive, social-media native | Price + peer adoption | Instagram Stories, campus ambassador, study group WhatsApp share |
| Young Professionals | Age 25–38, values-driven, Abdali/Shmeisani corridor | Ethics + reliability | LinkedIn organic, Instagram, Wasel Pass subscription |
| Female Riders | All ages, safety is primary decision factor | Safety + known driver before boarding | Family WhatsApp networks, female micro-influencers, driver profile visibility |
| Boycott-Motivated | Mixed age, politically aware, social-media active | Local ownership and ethics | Twitter/X, Instagram, Monthly Fairness Report shares |

University campuses are your highest-density, highest-virality rider channel. Find one "connector" student per campus — the person who organises events, runs the carpooling group, is central in the social network. Ask your first rider sign-ups who they know. Give each connector 30 printed invite cards with a personal referral code. When a friend signs up, the connector earns 1 free month of Wasel Go. No app required to share — just a QR code link.

Female rider acquisition runs through family WhatsApp networks. The "live trip sharing" feature — one tap, sends a live location link to a contact via WhatsApp — is worth more than any paid campaign. Win the mother's trust and you win the household. Every safety signal (driver profile visibility, SOS button prominence, vehicle inspection badge) is a female rider acquisition tool.

The boycott positioning: mention it once, clearly, then pivot to Wasel's own merits immediately. "Unlike platforms with overseas ownership, Wasel is Jordanian-owned — your money stays in Jordan and goes to the driver." Then: "Our drivers earn 30% more. Our fares are 5% below market. Our subscriptions give you benefits no other platform offers." Saying it twice is principled. Three times is propaganda.

3.4  PROMOTIONS & INCENTIVE DESIGN

Every promotion must simultaneously reduce acquisition friction, create a reason to share, and reinforce Wasel's positioning as a fair community-owned platform.

Promotion 1 — The Founding Driver Badge (Mu'assis): The first 500 drivers who complete registration and inspection receive a permanent "Mu'assis" badge on their profile — numbered, visible to every rider. The number creates scarcity, the badge creates identity, and together they create a story drivers tell for years. Physical badge also mailed. Cost: JD 1,000 total (JD 2/unit × 500). Highest ROI promotion in this plan.

Promotion 2 — Waitlist Position Discount: Every sign-up receives a position number determining their subscription discount. The mechanic self-seeds referrals without requiring a formal programme — every person has an immediate reason to share their link before better positions are taken.

Promotion 3 — Driver Referral Ladder: Refer 1 verified driver = 1 free subscription month. Refer 3 = 3 free months plus a referral badge. Refer 5+ = 6 free months plus a Wasel jacket plus your name in the Monthly Fairness Report. Activation condition: referred driver must complete inspection, pay first month, complete 10+ trips. Prevents gaming.

Promotion 4 — Cross-Side Referral: When a rider refers a verified driver → rider gets 2 months Wasel Pass free (JD 20 value). When a driver refers a rider → rider gets 1 month Wasel Go free, driver gets JD 5 off next subscription. Rider reward is large because finding a qualified driver is genuinely valuable work.

Promotion 5 — City Zero: The first 50 drivers and first 100 riders in each expansion city receive permanent "City Zero" status — a city-specific Founding Member number and 3-month discount. The pitch: "Be the person who brought Wasel to [city]." In Jordan, where regional identity is strong, this creates genuine city ambassadors.

3.5  SIGN-UP MECHANICS AND FUNNELS

The sign-up flow must be completable in under 90 seconds via WhatsApp, with no app download required at step one. App installation is the last step, not the first.

WhatsApp driver sign-up sequence: (1) Driver receives or scans a shared link. Opens a mobile web form — not the app. (2) Form: name, phone (pre-filled from WhatsApp), city, vehicle type, current platform (Yes/No). Four to five taps, under 90 seconds. (3) Immediate WhatsApp reply from Wasel business account: "Welcome [Name]. You are Founder #247. Your discount is locked in. Send a photo of your licence plate to complete registration." (4) Inspection booked via WhatsApp reply — driver sends preferred time. (5) Only after passing inspection does the driver receive an app download link with a pre-configured account.

Landing page principles: no hero video, no background animation, no corporate polish — these slow the page and signal the kind of inauthenticity that triggers Jordanian skepticism. Above the fold: a live counter ("Founder #247 of 500"), two name/phone fields, one button. Section 2: the earnings calculator (JD numbers, drag slider for daily trips). Section 3: three sentences on how it works. Section 4: trust signals only — LTRC licence number, company registration, physical address with Google Maps link, founding team photos with real names. Footer: a WhatsApp number that a real person answers. That one thing builds more trust than everything else on the page combined.

3.6  ACQUISITION BUDGET SCENARIOS

| Channel | ~$5K Budget | ~$20K Budget | ~$50K Budget |
| --- | --- | --- | --- |
| Field ambassadors + taxi office visits + printed materials | JD 700 | JD 1,400 | JD 2,800 |
| Founding Driver Badge production | JD 1,000 | JD 1,000 | JD 1,000 |
| Driver referral programme credits | JD 600 | JD 3,000 | JD 5,000 |
| University campus ambassadors (per semester) | JD 270 | JD 810 | JD 1,350 |
| Rider referral programme credits | JD 500 | JD 2,000 | JD 4,000 |
| Landing page development + hosting | JD 400 | JD 400 | JD 400 |
| Paid Facebook/Instagram ads (lookalike) | — | JD 3,800 | JD 8,000 |
| TikTok content production | — | JD 600 | JD 1,500 |
| OOH — Amman billboards (5–10) | — | — | JD 5,000 |
| Micro-influencer partnerships (3) | — | — | JD 3,000 |
| Driver earnings guarantee (first 50 drivers) | — | — | JD 2,500 |
| Founding Driver Gathering (100 drivers, dinner) | — | — | JD 1,800 |
| EXPECTED OUTPUT | ~100 drivers ~200 riders | ~300 drivers ~800 riders | ~600 drivers ~2,500 riders |

| KEY INSIGHT | The highest-leverage single growth lever in Jordan is the taxi office manager network. One converted manager yields 10–25 committed drivers at a cost of one visit and a glass of tea. Uber cannot replicate this because their model is designed to eliminate the middlemen. Wasel's advantage is making them partners. |
| --- | --- |

# 4. Workstreams & Owners

All execution activity is organised into eight workstreams. Acquisition is now a named workstream with its own dedicated tasks and owner — it is not a subset of Marketing.

| Workstream | Owner | Key Deliverables | Headcount | Phase Peak | Budget % |
| --- | --- | --- | --- | --- | --- |
| Legal | External Counsel + Founder | LTRC licence, T&Cs, PDPL, insurance | 1 (outsourced) | P0–P1 | 4% |
| Technology | CTO | 10 sprints, app stores, infra scaling | 5–8 (vendor + in-house) | P1 | 26% |
| Operations | COO | Zone management, driver ops, SLA, airport | 3–5 | P3–P4 | 12% |
| Driver Relations | 2× Driver Rel Officers | M0/M1/M2 onboarding, training, retention | 2–4 | P2–P4 | 8% |
| Acquisition | Marketing Lead + Driver Rel | Waitlist, taxi offices, campus ambassadors, referral ladders | 2–3 | P0–P3 | 10% |
| Marketing & Brand | Marketing Lead | Brand, campaigns, Fairness Reports, PR, OOH | 2–3 | P3–P4 | 12% |
| Finance | CFO (part-time → full-time P4) | Seed close, reporting, Series A data room | 1–2 | P0, P5 | 6% |
| People & Org | Founder | Hiring, culture, compensation benchmarking | 1 | P0, P4 | 22% |

HEADCOUNT BUILD PLAN

| Phase 0 (M1–M2) | 3 hires: Ops Manager, CX Lead, Marketing Lead → Total: 4 including Founder |
| --- | --- |
| Phase 1 (M2–M5) | 4 hires: CTO (or VP Eng), 2 Driver Rel Officers, 1 Data Analyst → Total: 8 |
| Phase 2 (M5–M7) | No new hires — consolidate and train existing team |
| Phase 3 (M7–M10) | 2 hires: 1 CX Agent, 1 B2B Sales Exec → Total: 10 |
| Phase 4 (M10–M12) | 3 hires: 2 Driver Rel Officers, 1 Finance Analyst → Total: 13 |
| Phase 5 (M12+) | 2–3 hires assessed pending Series A close |

# 5. Phase Plan & Stage Gates

Execution is divided into six phases. Each phase ends at a Stage Gate — a formal go/no-go decision point assessed by the founding team and lead investor. Failing a Stage Gate triggers a 2-week remediation sprint before re-assessment. Do not proceed to the next phase until the current Stage Gate is passed.

| P0 | Foundation ¦ Months 1–2 ¦ Budget: JD 8,600 |
| --- | --- |
| Legal incorporation, LTRC application, bank account, seed roadshow launch, vendor RFP and selection, founding driver ambassador recruitment. Stage Gate 0 (informal): seed committed, legal structure in place, LTRC application filed, 5 ambassadors recruited. |  |

| P1 | Build ¦ Months 2–5 ¦ Budget: JD 62,000 |
| --- | --- |
| 10 development sprints delivering driver app, rider app, admin dashboard, payment integration, app store submissions. Team hiring, brand identity, driver waitlist to 200+, rider waitlist to 400+. STAGE GATE 1: apps approved on stores, LTRC licence confirmed, 50+ driver waitlist active, team at 8 FTE. |  |

| P2 | Driver Onboarding ¦ Months 5–7 ¦ Budget: JD 22,000 |
| --- | --- |
| First 30 M0 drivers onboarded (free trial); M0→M1→M2 cohort ramp; rider pre-registration "Save Your Seat" campaign; Monthly Fairness Report #1 published. STAGE GATE 2: 80+ active verified drivers, app stable, media coverage secured, 500+ rider pre-signups. |  |

| P3 | Soft Launch ¦ Months 7–10 ¦ Budget: JD 48,000 |
| --- | --- |
| Public soft launch with 500 invite codes; war-room ops; referral programme live; Wasel Pass open; influencer partnerships; v1.1 and v1.2 releases; driver milestone event. STAGE GATE 3: 200+ active drivers, 1,000+ riders, revenue tracking vs model, NPS >50. |  |

| P4 | Full Launch ¦ Months 10–12 ¦ Budget: JD 98,000 |
| --- | --- |
| Remove invite gates; paid media; OOH campaign; airport corridor; corporate accounts; Series A data room. STAGE GATE 4: 400+ drivers, 5,000+ riders, monthly revenue JD 35K+, NPS >60. |  |

| P5 | Scale & Series A ¦ Month 12 ¦ Budget: JD 130,000 |
| --- | --- |
| Series A roadshow; second-city soft launch; v2.0 planning; LTRC renewal; annual audit. STAGE GATE 5: Series A term sheet received OR bridge plan approved; second city stable; 600+ drivers. |  |

# 6. Week-by-Week Execution Plan

The table below details all tasks across all 52 weeks and 8 workstreams, including the Acquisition workstream. Phase colour coding: P0 = Amber · P1 = Blue · P2 = Green · P3 = Pink · P4 = Purple · P5 = Red. Period labels: M = Month, W = Week number.

| Wk | Period | Workstream | Key Task / Deliverable | Owner | Budget |
| --- | --- | --- | --- | --- | --- |
| 1 | M1·W1 | Legal | Incorporate company; appoint legal counsel; open corporate bank account | Founder/Legal | JD 500 |
| 1 | M1·W1 | Finance | Draft fundraising materials; update investor deck with revised model figures | Founder/CFO | — |
| 1 | M1·W1 | Acquisition | Identify 5 founding driver ambassadors personally; build driver WhatsApp nucleus group | Founder | — |
| 2 | M1·W2 | Legal | File LTRC operator licence application; prepare JD 25K bank guarantee documentation | Legal | JD 2,500 |
| 2 | M1·W2 | Finance | Launch seed round roadshow; first investor meetings | Founder | — |
| 2 | M1·W2 | Acquisition | Visit 10 taxi office managers in person; deliver earnings comparison sheets | Founder/Ops | JD 100 |
| 3 | M1·W3 | Legal | Register PDPL data protection compliance; draft driver and rider T&Cs | Legal | JD 300 |
| 3 | M1·W3 | Ops | Define Amman pilot zone boundaries (North Amman — Abdoun, Sweifieh, Khalda, 7th Circle) | COO | — |
| 3 | M1·W3 | Acquisition | Launch driver waitlist landing page (WhatsApp-optimised, 3G-fast); activate @WaselJO social presence | CTO/Marketing | JD 400 |
| 4 | M1·W4 | Tech | Issue RFPs for app development; evaluate vendors; select development partner | CTO | — |
| 4 | M1·W4 | Acquisition | Field ambassador sessions begin at 3 fuel stations during peak hours (7–9am, 4–7pm) | Driver Rel | JD 100 |
| 4 | M1·W4 | Finance | Finalise employment contracts for founding team hires | HR/Legal | — |
| 5 | M2·W5 | Finance | Close seed round; wire funds; set up financial reporting cadence | CFO/Founder | — |
| 5 | M2·W5 | Tech | Sign development contract; kick off sprint planning; set up GitHub, Jira, Figma | CTO | JD 1,200 |
| 5 | M2·W5 | Acquisition | Founding Driver Badge (Mu'assis) programme activated; first badge issued to first sign-up | Marketing | JD 200 |
| 6 | M2·W6 | Legal | LTRC follow-up; submit any outstanding documentation; register vehicles list | Legal | JD 500 |
| 6 | M2·W6 | People | Hire Ops Manager, CX Lead, Marketing Lead (3 full-time) | Founder | JD 3,600 |
| 6 | M2·W6 | Acquisition | Driver referral ladder activated; WhatsApp group seeding begins in driver community groups | Ops/Driver Rel | JD 300 |
| 7 | M2·W7 | Tech | Sprint 1: Architecture setup, authentication, user registration, map SDK integration | CTO/Dev Team | JD 4,000 |
| 7 | M2·W7 | Brand | Finalise visual identity — logo, Arabic/English typography, brand guidelines | Marketing | JD 1,500 |
| 7 | M2·W7 | Acquisition | Rider waitlist page soft-launched (no promotion yet); Facebook organic content for driver groups begins | Marketing | — |
| 8 | M2·W8 | Tech | Sprint 2: Driver app core — trip request, accept, navigate flow; subscription billing module | Dev Team | JD 4,000 |
| 8 | M2·W8 | Acquisition | Fuel station ambassador programme scaled to 5 stations; 50+ driver sign-ups targeted by end of week | Driver Rel | JD 200 |
| 9 | M3·W9 | Tech | Sprint 3: Rider app — booking, real-time tracking, payment integration (CliQ/Visa) | Dev Team | JD 4,000 |
| 9 | M3·W9 | Ops | Map Amman zones; define service hours (6am–2am); draft driver standard operating procedures | COO | JD 400 |
| 9 | M3·W9 | Acquisition | University campus ambassador programme launched — 3 campuses; printed invite cards distributed | Marketing | JD 270 |
| 10 | M3·W10 | Tech | Sprint 4: Admin dashboard — driver KYC, subscriptions, analytics; push notification system | Dev Team | JD 4,000 |
| 10 | M3·W10 | Acquisition | TikTok content production — first 2 driver testimonial videos filmed; WhatsApp group at 80+ members | Marketing | JD 400 |
| 11 | M3·W11 | Tech | Sprint 5: Rating and review system; in-app chat; SOS emergency button; accessibility features | Dev Team | JD 4,000 |
| 11 | M3·W11 | Finance | Set up accounting system; implement payroll for 3 staff; monthly reporting template | CFO | JD 400 |
| 12 | M3·W12 | Tech | Sprint 6: Surge pricing cap logic; Wasel Pass and Go perk activation; cancellation policy engine | Dev Team | JD 4,000 |
| 12 | M3·W12 | Legal | Receive LTRC licence (expected); sign fleet insurance policy | Legal | JD 2,200 |
| 13 | M4·W13 | Tech | Sprint 7: Full integration testing; load testing (target 500 concurrent); bug backlog triage | Dev/QA | JD 4,000 |
| 13 | M4·W13 | Ops | Driver vehicle inspection protocol established; partner with 2 garages for certified inspections | COO | JD 800 |
| 13 | M4·W13 | Acquisition | Driver sign-up count review — target 200 by end of Month 4; paid Facebook ads to lookalike audiences activated if organic is below pace | Marketing | JD 800 |
| 14 | M4·W14 | Tech | Sprint 8: iOS App Store and Google Play Store submissions; beta build release (internal) | CTO | JD 4,000 |
| 14 | M4·W14 | Marketing | Branded merch design (car decals, driver uniforms, phone mounts); order print run | Marketing | JD 2,400 |
| 15 | M4·W15 | Tech | Sprint 9: App Store review cycle; address feedback; prepare v1.0 release candidate | Dev/CTO | JD 4,000 |
| 15 | M4·W15 | Ops | Define driver support SLA (response <2h); set up WhatsApp Business driver helpline | Ops Mgr | JD 300 |
| 15 | M4·W15 | Acquisition | Rider referral mechanic live — "Invite a Friend" via WhatsApp one-tap share; campus ambassador rewards active | Marketing | JD 500 |
| 16 | M4·W16 | Tech | Sprint 10: Final UAT with 10 internal testers; fix all P0/P1 bugs; tag v1.0.0 | QA/Dev | JD 4,000 |
| 16 | M4·W16 | Finance | Board update; investor report; cash flow vs budget reconciliation | CFO | — |
| 17 | M5·W17 | People | Hire CTO (or VP Eng), 2 Driver Relationship Officers, 1 Data Analyst | Founder/HR | JD 2,400 |
| 17 | M5·W17 | Acquisition | Pre-launch driver recruitment campaign — Facebook, WhatsApp groups, petrol stations; Mechanic shop partnership materials placed | Marketing | JD 1,500 |
| 18 | M5·W18 | Tech | Apps approved and live on stores (invite-only); backend infrastructure scaled to production | CTO | JD 1,500 |
| 18 | M5·W18 | Ops | STAGE GATE 1: Tech approved, LTRC licence confirmed, 50+ drivers waitlisted, team 8 FTE | Founder | — |
| 19 | M5·W19 | Driver | M0 cohort onboarding begins — 30 drivers, free trial month; KYC, vehicle inspection, app training | Driver Rel | JD 1,200 |
| 19 | M5·W19 | Acquisition | Boycott tailwind content campaign activated — "Fair Ride" organic posts; Monthly Fairness Report #1 drafted | Marketing | JD 1,500 |
| 20 | M5·W20 | Driver | Driver onboarding sessions (3 group sessions); distribute branded kits; issue app credentials | Driver Rel | JD 600 |
| 20 | M5·W20 | Acquisition | Press outreach — local media pitch on "Fair Ride" story; briefing document prepared | Marketing | JD 800 |
| 21 | M6·W21 | Driver | Week 3 M0 feedback loop — survey all 30 drivers; identify friction; deploy app hotfixes | CTO/Driver Rel | JD 2,000 |
| 21 | M6·W21 | Ops | Internal ride testing — 20 employee testers; measure dispatch time and ETA accuracy | COO | — |
| 22 | M6·W22 | Driver | Open driver waitlist to general public; target 100 total applications by end of week | Marketing/Ops | JD 1,800 |
| 22 | M6·W22 | Finance | Month 6 financials; confirm burn rate; update 12-month runway projection | CFO | — |
| 23 | M6·W23 | Driver | M0 → M1 conversion: 20 drivers move to JD 10/month ramp tier; 10 churn expected | Driver Rel | JD 200 |
| 23 | M6·W23 | Acquisition | Rider pre-registration campaign — "Save Your Seat" viral WhatsApp loop; target 500 pre-signups | Marketing | JD 2,500 |
| 24 | M6·W24 | Driver | M1 onboarding — 30 new drivers; run parallel sessions; target 50+ active M0/M1 drivers | Driver Rel | JD 600 |
| 24 | M6·W24 | Ops | Activate Wasel Go priority dispatch perk — tested in parallel with driver cohort | CTO/COO | JD 300 |
| 25 | M7·W25 | Driver | Safety audit — re-inspect top 20 M0 drivers; certify pass/fail; distribute Wasel window stickers | Ops Mgr | JD 400 |
| 25 | M7·W25 | Acquisition | Monthly Fairness Report #1 published — real driver earnings, trip counts, zero-commission proof | Marketing/Data | JD 600 |
| 26 | M7·W26 | Ops | STAGE GATE 2: 80+ active drivers, app stable, media coverage secured, 500+ rider pre-signups | Founder | — |
| 26 | M7·W26 | Finance | Q2 management accounts; board deck update; Series A timeline confirmed | CFO | — |
| 27 | M7·W27 | Launch | SOFT LAUNCH: 500 invite codes released; PR push; founder interview on local TV | Founder/Marketing | JD 5,000 |
| 27 | M7·W27 | Ops | War room — 3 ops staff monitoring real-time; 1-hour SLA; daily standup 8am | COO | — |
| 28 | M7·W28 | Tech | Monitor crash rates, API latency, dispatch success; deploy patches within 24h | CTO | JD 1,500 |
| 28 | M7·W28 | Acquisition | Referral programme live — "Invite a Friend, Both Get Wasel Go Free for 1 Month" | Marketing | JD 3,000 |
| 29 | M8·W29 | Driver | M1 → M2 conversion push — drivers earning >JD 50 net/week offered Standard tier (JD 20/mo) | Driver Rel | JD 400 |
| 29 | M8·W29 | Ops | Dispatch algorithm review — adjust radius and acceptance rate logic; target 85% success rate | CTO/COO | JD 800 |
| 30 | M8·W30 | Rider | Open Wasel Pass subscriptions (JD 10/month); "First Month Free" for early adopters | Marketing | JD 2,000 |
| 30 | M8·W30 | Finance | Month 8 close — first real revenue recognised; compare actuals to model | CFO | — |
| 31 | M8·W31 | Marketing | 3 Jordanian micro-influencer partnerships (80K–200K followers); document first Wasel rides | Marketing | JD 2,500 |
| 31 | M8·W31 | Tech | v1.1 release — improved ETA accuracy, dark mode, Arabic RTL polish, onboarding A/B test | Dev Team | JD 4,000 |
| 32 | M9·W32 | Driver | Driver Milestone Event — celebrate 100 active drivers; awards ceremony; media coverage | Ops/Marketing | JD 1,200 |
| 32 | M9·W32 | Ops | Expand pilot zone — add Jabal Amman, Ras Al Ain, Wadi Seer to service coverage | COO | JD 300 |
| 33 | M9·W33 | Marketing | Monthly Fairness Report #2; "1,000 rides" milestone post; community AMA on Instagram | Marketing | JD 600 |
| 33 | M9·W33 | Finance | Investor update — KPIs vs projections; revise 12-month model; identify bridge needs | Founder/CFO | — |
| 34 | M9·W34 | Tech | v1.2 release — scheduled rides, multi-stop trips, receipt export, improved map rendering | Dev Team | JD 4,000 |
| 34 | M9·W34 | Ops | SLA audit — review all complaints; analyse driver churn reasons; adjust onboarding script | Ops Mgr | — |
| 35 | M10·W35 | Driver | M2 → M3 upgrade campaign — top earners offered Plus (JD 35/mo) and Pro (JD 55/mo) tiers | Driver Rel | JD 300 |
| 35 | M10·W35 | Acquisition | Corporate accounts outreach — target 10 SMEs for employee transport; first B2B proposals sent | Founder/Marketing | JD 1,500 |
| 36 | M10·W36 | Ops | STAGE GATE 3: 200+ active drivers, 1,000+ riders, revenue vs model ✓, NPS >50 | Founder | — |
| 37 | M10·W37 | Launch | FULL AMMAN LAUNCH — Remove invite gates; open app to all; paid media live (Google, Meta, TikTok) | Marketing/CTO | JD 8,000 |
| 37 | M10·W37 | Driver | Aggressive driver recruitment — target 500 total drivers; JD 50 sign-on incentive | Driver Rel | JD 5,000 |
| 38 | M10·W38 | Tech | Scale infrastructure — AWS auto-scaling; CDN for map tiles; circuit breakers | CTO | JD 3,000 |
| 38 | M10·W38 | Marketing | OOH campaign — 10 Amman billboards; bus shelter ads (Mecca St, University St, 7th Circle) | Marketing | JD 6,000 |
| 39 | M11·W39 | Rider | Wasel Business tier launch — JD 25/month, 50 rides, no surge, central billing | Founder/Ops | JD 1,000 |
| 39 | M11·W39 | Finance | Month 9 close — target JD 30K+ revenue; bridge financing documents prepared if needed | CFO | — |
| 40 | M11·W40 | Ops | Airport corridor activation — dedicated Wasel zone; partner with terminal management | COO | JD 2,000 |
| 40 | M11·W40 | Marketing | Monthly Fairness Report #3; "10,000 rides" milestone campaign; user testimonial videos | Marketing | JD 1,500 |
| 41 | M11·W41 | Tech | v1.3 release — Wasel Business portal, scheduled corporate pickups, Arabic support centre | Dev Team | JD 4,000 |
| 41 | M11·W41 | Driver | Driver welfare programme — bank loan product partnership; monthly wellness check-ins | Ops Mgr | JD 800 |
| 42 | M11·W42 | Legal | LTRC licence renewal due diligence; annual report submission; update driver registry | Legal | JD 1,000 |
| 42 | M11·W42 | Finance | Series A preparation — appoint financial advisor; build data room (actuals + projections) | CFO/Founder | JD 2,000 |
| 43 | M12·W43 | Marketing | Holiday season campaign planning — special promotions for high-demand travel period | Marketing | JD 2,000 |
| 43 | M12·W43 | Ops | Pilot expansion scoping — second-city market assessment and regulatory requirements mapping | COO | JD 1,200 |
| 44 | M12·W44 | People | Year-end review; salary benchmarking; hire Year 2 roles (2 Driver Rel, 1 Finance Analyst) | Founder/HR | JD 3,600 |
| 44 | M12·W44 | Finance | STAGE GATE 4: 400+ drivers, 5,000+ riders, monthly revenue JD 35K+, NPS >60 | Founder | — |
| 45 | M12·W45 | Finance | Series A roadshow begins — 15 VC/family office meetings; target close in Year 2 | Founder/CFO | — |
| 46 | M12·W46 | Tech | v2.0 planning — Pool rides, Ladies service, AI dispatch optimisation | CTO | JD 2,000 |
| 46 | M12·W46 | Ops | Second-city soft launch preparation — driver recruitment starts; 20 drivers waitlisted | COO | JD 1,500 |
| 47 | M12·W47 | Marketing | Monthly Fairness Report #4; "50,000 rides" milestone campaign; documentary short film | Marketing | JD 3,000 |
| 47 | M12·W47 | Finance | Year-end audit; statutory filing; board approval of annual accounts | CFO/Auditor | JD 3,500 |
| 48 | M12·W48 | Tech | Data platform build — event tracking, cohort analysis, driver/rider LTV dashboards | Data/CTO | JD 2,500 |
| 48 | M12·W48 | Ops | Second-city launch — 20 drivers, invite-only, replicate North Amman playbook | COO | JD 3,000 |
| 49 | M12·W49 | Marketing | Peak season campaign prep — special rates, charity partnership tie-in | Marketing | JD 1,500 |
| 49 | M12·W49 | Finance | Series A due diligence support — data room access to 3 lead investors | CFO | — |
| 50 | M12·W50 | Tech | v2.0 Sprint 1 — Pool ride architecture; dynamic ride-matching algorithm design | CTO/Dev | JD 4,000 |
| 50 | M12·W50 | Ops | Annual operational review — driver satisfaction survey, NPS benchmarking, cost analysis | COO | — |
| 51 | M12·W51 | Finance | Year 2 Q1 budget approval; LTRC renewal payment (JD 100K); update 3-year model for Series A | CFO | JD 100,000 |
| 51 | M12·W51 | Marketing | Brand refresh assessment — Year 1 learnings; update Year 2 campaign messaging | Marketing | JD 1,000 |
| 52 | M12·W52 | Ops | STAGE GATE 5 / YEAR-END: KPI dashboard review; Series A readiness check; 600+ drivers | Founder | — |
| 52 | M12·W52 | Finance | Shareholder annual meeting; Year 1 financials; Year 2 strategy presentation | Founder/CFO | — |

# 7. Cost Model & Budget Breakdown

Total Year 1 budget: JD 472,000 (~$665K). All figures in Jordanian Dinars. Personnel costs include NSSF employer contribution at 21.75%. Acquisition budget is broken out separately from Marketing to reflect the dedicated workstream.

| Cost Category | P0 | P1 | P2 | P3 | P4 | P5 + Total |
| --- | --- | --- | --- | --- | --- | --- |
| Personnel (salaries + NSSF) | 8,700 | 28,000 | 19,200 | 26,400 | 36,000 | 24,000 / 142,300 |
| Technology (development + infra) | 1,200 | 42,500 | 2,300 | 12,000 | 8,000 | 8,500 / 74,500 |
| Acquisition (pre-launch driver & rider) | 2,000 | 5,000 | 7,000 | 8,000 | 3,000 | — / 25,000 |
| Marketing & Brand (post-launch campaigns) | 600 | 2,800 | — | 6,600 | 16,000 | 5,500 / 31,500 |
| Legal & Regulatory | 3,800 | 2,700 | — | — | 1,500 | — / 8,000 |
| Operations & Driver Relations | — | 1,100 | 2,600 | 3,200 | 10,000 | 4,500 / 21,400 |
| Finance & Professional Services | 400 | 800 | — | — | 2,000 | 3,500 / 6,700 |
| LTRC Licence Fee | — | — | — | — | — | 100,000 / 100,000 |
| Bank Guarantee (one-time) | 25,000 | — | — | — | — | — / 25,000 |
| Contingency (5%) | 2,100 | 4,200 | 1,500 | 2,800 | 3,800 | 2,500 / 16,900 |
| TOTAL | 43,800 | 87,100 | 32,600 | 59,000 | 80,300 | 148,500 / JD 451,300 |

REVENUE & P&L SUMMARY

| Driver Subscription Revenue (Year 1) | JD 154,000 |
| --- | --- |
| Rider Subscription Revenue (Year 1) | JD 130,000 |
| TOTAL REVENUE (Year 1) | JD 284,000 |
| Total Operating Cost (Year 1) | JD 451,300 |
| Net Operating Loss (Year 1) | JD (167,300) |
| Seed Raise Target | JD 472,000 (~$665K USD) |
| Implied Runway | ~14 months from seed close to Stage Gate 5 |

# 8. KPI Dashboard Specification

25 metrics across five categories. All metrics reported weekly to the founding team and monthly to investors. Dashboard tooling: Google Sheets (Phases 0–2) then Metabase + PostgreSQL (Phase 3+).

GROWTH KPIS

| Metric | P3 Target | P4 Target | P5 Target | Source |
| --- | --- | --- | --- | --- |
| Active Drivers (≥1 trip/week) | 200 | 400 | 600+ | Admin dashboard |
| Registered Riders | 1,000 | 5,000 | 8,000 | App DB |
| Monthly Active Riders (MAR) | 600 | 3,000 | 5,000 | App DB |
| Driver MoM Growth Rate | 15% | 20% | 10% | Admin dashboard |
| Rider MoM Growth Rate | 25% | 28% | 15% | App DB |
| Waitlist-to-Active Driver Conversion | ≥60% | ≥65% | ≥70% | CRM pipeline |

REVENUE & UNIT ECONOMICS KPIS

| Metric | P3 Target | P4 Target | P5 Target | Source |
| --- | --- | --- | --- | --- |
| Monthly Revenue (JD) | 12,000 | 35,000 | 48,000 | QuickBooks |
| Driver Subscription Attach Rate | 60% | 70% | 75% | Admin dashboard |
| Rider Subscription Attach Rate | 35% | 40% | 42% | App DB |
| ARPU — Driver (monthly) | JD 18 | JD 24 | JD 28 | QuickBooks |
| ARPU — Rider (monthly) | JD 4.20 | JD 5.50 | JD 6.00 | QuickBooks |
| Monthly Burn Rate | < JD 55K | < JD 70K | < JD 80K | QuickBooks |
| Cash Runway (months) | > 8 | > 6 | > 4 | CFO dashboard |

ACQUISITION KPIS

| Metric | P1 Target | P2 Target | P3 Target | Source |
| --- | --- | --- | --- | --- |
| Driver Waitlist Sign-ups | 200 | 350 | 500+ | CRM |
| Rider Waitlist / Pre-registrations | 400 | 800 | 2,000+ | CRM |
| Taxi Office Partnerships | 5 | 12 | 20 | Ops log |
| Referral Conversion Rate (driver) | 40% | 50% | 55% | CRM |
| Driver CAC (blended, JD) | < 15 | < 12 | < 10 | Finance |
| Rider CAC (blended, JD) | < 8 | < 6 | < 5 | Finance |

OPERATIONS KPIS

| Metric | P3 Target | P4 Target | P5 Target | Source |
| --- | --- | --- | --- | --- |
| Dispatch Success Rate | 80% | 88% | 92% | Backend analytics |
| Average ETA (minutes) | < 8 | < 6 | < 5 | App telemetry |
| Driver Average Rating | ≥ 4.5 | ≥ 4.6 | ≥ 4.7 | App DB |
| Driver Monthly Churn | < 12% | < 9% | < 7% | Admin dashboard |
| Rider Retention (Month + 1) | 40% | 50% | 60% | Metabase cohort |
| App Crash Rate | < 0.5% | < 0.3% | < 0.2% | Firebase Crashlytics |

BRAND & COMMUNITY KPIS

| Metric | P3 Target | P4 Target | P5 Target | Source |
| --- | --- | --- | --- | --- |
| Net Promoter Score | > 50 | > 60 | > 65 | Post-trip survey |
| Instagram Followers (@WaselJO) | 5,000 | 20,000 | 40,000 | Instagram Insights |
| Monthly Fairness Report Views | 500 | 3,000 | 7,000 | Google Analytics |
| Corporate Accounts Signed | 0 | 5 | 15 | CRM |

# 9. Risk Register

Risk Score = Likelihood (1–5) × Impact (1–5). Score ≥ 15 = Critical (red); 8–14 = High (amber); < 8 = Moderate (green). All Critical and High risks have a named owner and explicit mitigation plan.

| ID | Risk | Like. | Impact | Score | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- | --- |
| R01 | LTRC licence delayed beyond Phase 1 | 3 | 5 | 15 | Apply in Month 1; CEO direct liaison; prepare escalation letter; legal counsel on standby | Founder/Legal |
| R02 | Seed round not closed by Month 2 | 3 | 5 | 15 | 3 angel investors pre-committed; JD 50K founder bridge available; Phase 1 spend reduced 20% if needed | Founder |
| R03 | Driver sign-ups high but activation low — curiosity leads not commitment | 4 | 4 | 16 | 70% of driver sign-ups must come from personal-chain channels; 48h WhatsApp follow-up on every sign-up; inspection completion is the primary pipeline metric | Founder/Ops |
| R04 | Anti-incumbent tailwind fades before launch | 3 | 4 | 12 | Accelerate Phase 2 by 2 weeks if sentiment data shows decline; invest in owned content and Monthly Fairness Reports | Marketing |
| R05 | Driver churn > 15%/month in Phase 2 | 3 | 4 | 12 | Weekly earnings transparency; driver WhatsApp daily support; extend M1 trial if needed | Driver Rel |
| R06 | App rejected from App Store/Play Store | 2 | 5 | 10 | Submit in Month 4; dedicated QA pass; TestFlight beta for rapid deployment fallback | CTO |
| R07 | Rider acquisition cost exceeds JD 8/rider | 3 | 3 | 9 | Optimise referral viral loop; shift budget to WhatsApp organic; pause paid media if CAC > JD 10 | Marketing |
| R08 | Incumbent platform launches zero-commission promotion as response | 2 | 4 | 8 | Position on trust and local ownership, not just price; community loyalty programmes activated | Founder |
| R09 | Key hire fails (CTO vacancy) | 2 | 4 | 8 | Identify 3 backup candidates; maintain vendor as fallback; consider fractional CTO if needed | Founder |
| R10 | Cyberattack or data breach | 2 | 4 | 8 | ISO 27001 controls; penetration test before launch; PDPL-compliant DPA; cyber insurance | CTO |
| R11 | Jordan regulatory tightening (new LTRC rules) | 2 | 3 | 6 | LTRC relationship management; quarterly regulatory scan; legal counsel on retainer | Legal |
| R12 | Driver income below expectation causing churn | 2 | 3 | 6 | Pre-launch earnings simulator in driver app; 90-day earnings guarantee for first 50 drivers | Ops Mgr |

# 10. Launch Playbook — Day −14 to Day +14

The soft launch at the start of Month 7 is the most critical operational moment of Year 1. The following playbook governs all activity in the two weeks before and two weeks after launch. Day 0 = Soft Launch Day.

PRE-LAUNCH: DAYS −14 TO −8

| Day | Activity | Detail | Owner | Pass Criterion |
| --- | --- | --- | --- | --- |
| D−14 | Infrastructure stress test | Simulate 500 concurrent users; 1,000 trip requests/hour; check auto-scaling | CTO | Zero downtime, p99 < 3s |
| D−13 | Driver final safety check | Re-inspect all 80+ active drivers; vehicles, documents, app functionality | Driver Rel | 100% pass rate |
| D−12 | Invite code generation | Generate 500 unique codes; test redemption flow end-to-end | CTO/Ops | All 500 codes valid |
| D−11 | Press briefings | Brief local media under embargo; provide launch facts sheet; confirm interview slots | Marketing | 3+ outlets confirmed |
| D−10 | Driver launch briefing | Full team call with all 80+ drivers; launch protocol, support contacts, FAQ | COO/Driver Rel | 90%+ attendance |
| D−8 | Rider invite distribution | Send codes to 500 pre-registered riders via WhatsApp + SMS; activation instructions sent | Marketing/CTO | 200+ codes activated within 48h |

PRE-LAUNCH: DAYS −7 TO −1

| Day | Activity | Detail | Owner | Pass Criterion |
| --- | --- | --- | --- | --- |
| D−7 | War room setup | Configure Grafana dashboards, PagerDuty alerts, Slack ops channel | CTO | All alerts firing correctly |
| D−6 | Social pre-launch teaser | Post countdown content — "Something fair is coming to Amman" — on Instagram, Facebook, TikTok | Marketing | 500+ engagements |
| D−5 | Payment final test | End-to-end CliQ/Visa: 20 test transactions; refund flow; subscription billing cycle | CTO | Zero failed transactions |
| D−3 | Founder media interview | Pre-record TV segment; record Instagram Live; finalise key messages for launch day | Founder/Marketing | Segment confirmed for Day 0 |
| D−2 | Support team drill | Simulate 50 concurrent tickets; WhatsApp queue; measure response time | CX Lead | < 30 min avg response |
| D−1 | GO / NO-GO decision | Full team checklist: tech ✓, drivers ✓, legal ✓, cash ✓, media ✓. CEO final sign-off. | Founder | All 5 criteria met |

LAUNCH DAY (DAY 0)

| 06:00 | Open app to all 500 invite-code holders; pilot zone goes live |
| --- | --- |
| 07:00 | CEO Instagram Live — "Wasel is live. Fair rides start now." 30-minute Q&A |
| 08:00 | TV interview segment airs (pre-recorded) |
| 09:00 | First 100 trips milestone monitoring; war room tracking dispatch rate |
| 12:00 | Press articles published; share across all social channels |
| 16:00 | First daily debrief — crash rate, ETA, dispatch rate, complaints reviewed |
| 18:00 | Driver WhatsApp message — trip count, earnings update, thank-you from CEO |
| 21:00 | End-of-day report to investors — Day 1 metrics and media coverage roundup |

POST-LAUNCH: DAYS +1 TO +14

| Day | Activity | Detail | Owner | Pass Criterion |
| --- | --- | --- | --- | --- |
| +1 | Patch window | Any P0 bugs from Day 0 fixed and deployed by noon; no new features until D+3 | CTO | Zero P0 bugs outstanding |
| +2 | Rider experience survey | In-app survey to all Day 0 riders; target 100 responses | CX Lead | 100 responses, NPS > 40 |
| +3 | Referral programme launch | "Invite a Friend, Both Get Wasel Go Free for 1 Month" — automated WhatsApp share link | Marketing/CTO | 200+ links shared |
| +5 | Press follow-up | Send Day 1–5 metrics press release; pitch "1,000 rides" milestone story | Marketing | 1 follow-up article |
| +7 | Week 1 review | Full team review: dispatch, churn, complaints, driver satisfaction, revenue pace | Founder | Decision: scale or remediate |
| +10 | Wasel Pass open | Open Pass (JD 10/mo) subscriptions; "First Month Free" for first 200 sign-ups | Marketing/CTO | 100+ Pass sign-ups in 72h |
| +14 | Two-week review | Board deck: actuals vs plan; burn vs forecast; invite code expansion decision | Founder/CFO | Board approves expansion to 2,000 codes |

# 11. Final Deliverables Checklist

Track all major deliverables in real time. Owner updates status column weekly.

LEGAL & REGULATORY

| Deliverable | Owner | Phase | Period | Status |
| --- | --- | --- | --- | --- |
| Company incorporated | Legal/Founder | P0 | M1·W1 | [ ] |
| Bank account opened | CFO | P0 | M1·W1 | [ ] |
| LTRC licence application filed | Legal | P0 | M1·W2 | [ ] |
| Bank guarantee (JD 25K) lodged | CFO | P0 | M1·W2 | [ ] |
| Driver T&Cs and rider T&Cs finalised | Legal | P0 | M1·W3 | [ ] |
| PDPL data protection registration | Legal | P0 | M1·W3 | [ ] |
| LTRC licence received | Legal | P1 | M3 | [ ] |
| Fleet + liability insurance live | Legal/COO | P1 | M3 | [ ] |
| LTRC annual renewal + JD 100K fee | Legal/CFO | P5 | M12 | [ ] |

ACQUISITION

| Deliverable | Owner | Phase | Period | Status |
| --- | --- | --- | --- | --- |
| 5 founding driver ambassadors recruited | Founder | P0 | M1·W1 | [ ] |
| Driver waitlist landing page live | CTO/Marketing | P0 | M1·W3 | [ ] |
| Founding Driver Badge (Mu'assis) programme live | Marketing | P0 | M2·W5 | [ ] |
| 10 taxi office manager visits completed | Founder/Ops | P0–P1 | M1–M2 | [ ] |
| 200+ driver waitlist sign-ups | Acquisition | P1 | M4 | [ ] |
| 500 rider pre-registrations | Marketing | P2 | M7 | [ ] |
| Monthly Fairness Report #1 published | Marketing/Data | P2 | M7·W25 | [ ] |
| Wasel Pass subscriptions open | Marketing | P3 | M8 | [ ] |
| Corporate accounts programme launched | Founder/Ops | P4 | M11 | [ ] |

TECHNOLOGY

| Deliverable | Owner | Phase | Period | Status |
| --- | --- | --- | --- | --- |
| Development contract signed | CTO | P0 | M2·W5 | [ ] |
| Driver app core flow (Sprints 1–3) | Dev Team | P1 | M3 | [ ] |
| Rider app core flow | Dev Team | P1 | M3 | [ ] |
| Payment integration live (CliQ + Visa) | Dev Team | P1 | M3 | [ ] |
| iOS App Store approval | CTO | P1 | M5 | [ ] |
| Google Play Store approval | CTO | P1 | M5 | [ ] |
| v1.1 release (ETA accuracy, dark mode, Arabic) | Dev Team | P3 | M8 | [ ] |
| v1.2 release (scheduled rides, multi-stop) | Dev Team | P3 | M9 | [ ] |
| AWS auto-scaling live | CTO | P4 | M10 | [ ] |
| v1.3 release (Wasel Business portal) | Dev Team | P4 | M11 | [ ] |
| Metabase data platform live | Data/CTO | P5 | M12 | [ ] |

# 12. Appendix: Definitions and Glossary

DRIVER COHORT DEFINITIONS

| M0 (Trial) | Free trial month. Designed to de-risk the switch from incumbents. Target: 100% app activation within 48 hours of onboarding. |
| --- | --- |
| M1 (Ramp) | Month 2. Reduced fee of JD 10/month. Driver has proven the platform. Target: 60% of M0 convert. |
| M2 (Active) | Month 3+. Full subscription tier activated — Standard (JD 20/mo), Plus (JD 35/mo), or Pro (JD 55/mo). |
| M3 (Champion) | Drivers in M2 for 3+ months with rating ≥ 4.7. Eligible for Wasel Champion programme — featured in Fairness Reports, referral bonuses. |

TIER DEFINITIONS

| Wasel Go (Rider) | JD 5/month. Priority dispatch, surge cap (1.3×), 1 free cancellation per day. No fare discount. |
| --- | --- |
| Wasel Pass (Rider) | JD 10/month. All Go perks + 1 free ride/month (up to JD 5 value) + airport priority lane. |
| Wasel Business (Rider) | JD 25/month. Up to 50 rides/month, central billing, no surge, dedicated account manager. |
| Standard (Driver) | JD 20/month. 8 trips/day cap. Entry tier. |
| Plus (Driver) | JD 35/month. 11 trips/day cap. |
| Pro (Driver) | JD 55/month. 13 trips/day cap. Full daily earnings potential. |

GLOSSARY

| ARPU | Average Revenue Per User |
| --- | --- |
| CAC | Customer Acquisition Cost |
| CliQ | Jordan's instant bank-to-bank payment system |
| JD | Jordanian Dinar (pegged at 1 JD = $1.41 USD) |
| LTRC | Land Transport Regulatory Commission — licences ride-hailing operators in Jordan |
| LTV | Lifetime Value of a customer |
| MAR | Monthly Active Riders |
| Mu'assis | Arabic for "Founder" — the title given to the first 500 Wasel drivers |
| MoM | Month-over-Month |
| NPS | Net Promoter Score (−100 to +100; > 50 is excellent) |
| NSSF | National Social Security Fund — Jordan employer contribution at 21.75% |
| PDPL | Personal Data Protection Law — Jordan's data privacy regulation |
| P0–P5 | Execution phases 0–5 of the Wasel Year 1 roadmap |
| SLA | Service Level Agreement |
| Stage Gate | Formal go/no-go review at end of each phase |

WASEL

"To move Jordan forward — fairly."

Year 1 Master Plan · Version 1.1 · Confidential